## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16863 | Augmentation | Augmentation of DAKSHIN KHANDA (ZONE - IA) PWSS under Jal Jeevan Mission of Bharatpur-II Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000537/2023-2024 | 3146/MURD | 09/10/2023 | 28/10/2026 | DHIRENDRANATH MONDAL | 457.09 | 101.96 | 22.31 | 10
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16863 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dakshin Kanda Zone- I A Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000697/2023-2024 | 3782/MURD | 11/12/2023 | 01/09/2025 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16863 | Augmentation | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHAK RAMPRASAD and Dakshin Khanda Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000388/2023-2024 | 2778/MURD | 01/09/2023 | 15/09/2023 | SARKAR WATER SUPPLY AGENCY | 9.21 | 7.86 | 85.31 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16863 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 3.45 | 3.54 | 80
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16863 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at, Dakshinkhanda Zone-IA T.W-II, III, Zone-IB T.W-II, Dakshinkhanda Zone-II T.W- I, II Water Supply Scheme of Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000506/2024-2025 | 718/MURD | 25/03/2025 | 29/05/2025 | MAMATA USHA ENTERPRISE | 58.95 | 0 | 0 | 0
Total | [13 empty] | 641.18 | 113.28 | 17.67