## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16864 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-IA under Bhasaipaikar ground water based water supply scheme under Block_ Samserganj, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000246/2023-2024 | 3682/MEDB | 03/11/2023 | 03/02/2024 | CONCORD ENGINEERING | 34.17 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16864 | Augmentation | Supply of UPVC Pipe and RDS filter for the work of Sinking of (300 mm x 200 mm) dia Big dia tube well at Village Bhasaipaikar(313879) in connection with FHTC work of Bhasaipaikar(Zone-I) Water Supply Scheme of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000092/2022-2023 | 238/JSD | 05/05/2022 | 04/06/2022 | DIPAYAN DEY | 4.61 | 2.32 | 50.43 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16864 | Augmentation | Sinking of (300 mm x 200 mm) dia Big dia tube well 75 mtr. Deep by direct rotary rig method using UPVC Pipe and RDS filter at Village Bhasaipaikar(313879) in connection with FHTC work of Bhasaipaikar(Zone-I) Water Supply Scheme (Scheme ID- 0001723333) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000091/2022-2023 | 237/JSD | 05/05/2022 | 04/06/2022 | DIPAYAN DEY | 4.42 | 3.99 | 90.4 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16864 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 1167/MURD/12 | 28/04/2023 | 28/04/2023 | Resource Division | 73.37 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16864 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 12/11/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16864 | Augmentation | Preparation of Design, Drawing and Approved from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carrying Pipe, 600 mm dia 10 mm thick MS casing pipe and pushing of casing pipe by Hydraulic Jacking Technique method across at chainage 276+100 of the N.H- 34 of at Mouza-Ratanpur of Bhasaipaikar W/S Scheme under Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000824/2023-2024 | 745/MURD | 12/03/2024 | 10/06/2024 | M/S. GOUTAM ROY | 37 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16864 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 30/10/2024 | SANJAY BISWAS | 2012.72 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16864 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhasaipaikar Zone- I A & Kusumgachi Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000137/2023-2024 | 1772/MURD | 06/07/2023 | 31/12/2024 | R.K. DRILLING SERVICES | 27.67 | 3.18 | 11.48 | 100
Total | [13 empty] | 2228.92 | 9.49 | 0.43