## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. | SM/16866 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 18/08/2022 | APEX ENGINEERING | 9.6 | 1.72 | 17.93 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. | SM/16866 | Augmentation | Augmentation of BILASPUR PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000079/2023-2024 | 1385/MURD | 22/05/2023 | 02/03/2025 | ULTRA CONSTRUCTION. | 227.02 | 178.12 | 78.46 | 45
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. | SM/16866 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 1180/MURD/04 | 29/04/2023 | 29/04/2023 | Resource Division | 19.59 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. | SM/16866 | Augmentation | Renovation for Filter media of Existing IEP of (Capacity 51.38 Cum/hr.) in Bilaspur Water Supply Scheme of Domkal Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000077/2025-2026 | 1342/MURD | 11/06/2025 | 08/12/2025 | SK CONSTRUCTION (NAJIR SK.) | 11.97 | 0 | 0 | 100
Total | [13 empty] | 268.17 | 179.84 | 67.06