## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/16867 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 1075/MURD/10 | 19/04/2023 | 19/04/2023 | Resource Division | 2.47 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/16867 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur - I Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000626/2023-2024 | 3410/MURD | 02/11/2023 | 16/03/2025 | GENUINE | 18.43 | 0 | 0 | 100
3 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/16867 | New | CHHATRAPUR PWSS under Jal Jeevan Mission of BHARATPUR -I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000477/2023-2024 | 3034/MURD | 27/09/2023 | 01/09/2025 | MONDAL ENTERPRISE | 133.95 | 0 | 0 | 30
Total | [13 empty] | 154.84 | 0 | 0