## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/16867 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 1075/MURD/10 | 19/04/2023 | 19/04/2023 | Resource Division | 2.47 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/16867 | New | CHHATRAPUR PWSS under Jal Jeevan Mission of BHARATPUR -I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000477/2023-2024 | 3034/MURD | 27/09/2023 | 01/09/2025 | MONDAL ENTERPRISE | 133.95 | 0 | 0 | 30
Total | [13 empty] | 136.42 | 0 | 0