## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. | SM/16870 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-III under Bhasaipaikar ground water based water supply scheme under Block_ Samserganj ,Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000248/2023-2024 | 3660/MEDB | 03/11/2023 | 03/02/2024 | JOGMAYA ENGINEERING | 34.39 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. | SM/16870 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 1167/MURD/30 | 28/04/2023 | 28/04/2023 | Resource Division | 33.07 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. | SM/16870 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 12/11/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. | SM/16870 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 30/10/2024 | SANJAY BISWAS | 2012.72 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. | SM/16870 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Basudevpur halt Station (TP NO 240/8 & 240/9) at Ratanpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Bhasipaikar Zone - III ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000422/2021-2022 | 2479/MURD | 16/08/2021 | 15/10/2021 | ACQUA CONSTRACTION CONSORTIAM | 22.97 | 0 | 0 | 90
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. | SM/16870 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhasaipaikar Zone-III Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,Junior Engineer 3 | ORD/000692/2023-2024 | 3767/MURD | 08/12/2023 | 01/04/2025 | MAMATA USHA ENTERPRISE | 27.67 | 0 | 0 | 50
Total | [13 empty] | 2165.78 | 0 | 0