## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16986 | Retrofitting | Last mile connectivity and providing 1803 nos Funcational House Hold Connection from Zone- II of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 2,JUNIOR ENGINEER 6 | ORD/000329/2023-2024 | 2686/MURD | 25/08/2023 | 23/12/2023 | AJAY MONDAL | 114.49 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16986 | Retrofitting | Last mile connectivity and providing 5600 nos Functional House Hold Connection from Zone- XIII of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 2,JUNIOR ENGINEER 6 | ORD/000335/2023-2024 | 2692/MURD | 25/08/2023 | 23/12/2023 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 352.9 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16986 | Retrofitting | Allied work for Construction of Annular Combined Pile Raft Foundation for R.C.C Elevated Reservoir of Capacity 900 CuM of staging height 20 Meter at Head Work site within BANYESWAR(Zone-XIII) W/S Scheme, Block-Sagardighi, District-Murshidabad Under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION,JUNIOR ENGINEER 6 | ORD/000836/2023-2024 | 785/MURD | 14/03/2024 | 13/05/2024 | BIJAY CHOWDHURY | 84.81 | 0 | 0 | 85
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16986 | Retrofitting | Permission for laying pipeline (200 mm dia) along the NH-12 within the utility corridor from Moregram to gangadda of sagardighi surface water based drinking water supply scheme block sagardighi, district-Murshidabad under Murshidabad Division, P.H.E.Dte. |  |  | BILL/01075/2023-2024 | 543-MSD/2023-24 | 16/02/2024 | 16/02/2024 | CHIEF ENGINEER CIVIL MINISTRY OF ROAD TRANSPORT AND HIGHWAYS KOLKATA | 3.18 | 0 | 0 | 0
Total | [13 empty] | 555.38 | 0 | 0