## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/17389 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-II under Nagar ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000274/2023-2024 | 3714/MEDB | 03/11/2023 | 03/02/2024 | A.G. ENTERPRISE | 22.35 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/17389 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1004/MURD/6 | 11/04/2023 | 11/04/2023 | Resource Division | 24.92 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/17389 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 1167/MURD/15 | 28/04/2023 | 28/04/2023 | Resource Division | 20.22 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/17389 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Nagar Zone- II Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000717/2023-2024 | 3834/MURD | 14/12/2023 | 04/01/2024 | MAMATA USHA ENTERPRISE | 23.59 | 0 | 0 | 50
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/17389 | Augmentation | POWER CONNECTION AT PWSS PH 2 Z 2 NAGAR ID 304250316 |  |  | BILL/00181/2024-2025 | 36/WBSEDCL-JJM | 22/04/2024 | 22/04/2024 | WBSEDCL | 4.13 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/17389 | Augmentation | POWER CONNECTION AT PWSS NAGAR PH1 Z2 ID 304250315 |  |  | BILL/00180/2024-2025 | 35/WBSEDCL-JJM | 22/04/2024 | 22/04/2024 | WBSEDCL | 7.14 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/17389 | Augmentation | Augmentation of Ground Water Based Nagar Zone II PWSS of accommodate FHTC( 1909 Nos), Laying Distribution System, Laying Rising Main, Switch Room, Boundary Wall, 300 CUM OHR in Khargram Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000574/2023-2024 | 3299/MURD | 20/10/2023 | 01/12/2025 | CREATIVE CONSTRUCTION | 394.26 | 0 | 0 | 10
Total | [13 empty] | 496.62 | 0 | 0