## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 1210/MURD/09 | 02/05/2023 | 02/05/2023 | Resource Division | 48.45 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | Augmentation | Laying of Rising Main, Laying of Distribution System and Overhauling of RCC 180 Cum OHR for Augmentation of HILORA ZONE II Piped Water Supply Scheme in SUTI-I Block in Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000871/2022-2023 | 850/MURD | 24/03/2023 | 22/02/2026 | M H SUPPLIERS | 71.55 | 55.99 | 78.24 | 70
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone- I & Hilora Zone-II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000133/2023-2024 | 1769/MURD | 06/07/2023 | 27/07/2023 | R.K. DRILLING SERVICES | 18.45 | 18.18 | 98.57 | 100
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | Augmentation | Providing FHTC Connection to 1424 nos household, Special repair and renovation of existing 2 (Two) Nos Pump House & Alied Works and Repair of Boundary Wall (140m + 50m) =190 m at T/W-I site & T/W-II site for Augmentation of HILORA ZONE II Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000870/2022-2023 | 849/MURD | 24/03/2023 | 29/08/2025 | JAMIRUL CONSTRUCTION | 79.6 | 5.1 | 6.41 | 85
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | Augmentation | Allied work of laying of additional pipeline of 125 mm dia, Land Development, connecting road and construction of soakwell and construction of surface drain of 150 m lenth at Hilora zone 2 PWSS at suti -1 Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000021/2024-2025 | 1812/MURD | 20/06/2024 | 28/01/2026 | M H SUPPLIERS | 53.94 | 0 | 0 | 50
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HILORA Zone-II Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000054/2025-2026 | 1224/MURD | 28/05/2025 | 27/07/2025 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 23.01 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | Augmentation | Laying Distribution System and Road Restoration of Hilora Zone-II PWSS in Suti-I Block , Jangipur Sub-Division under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000075/2025-2026 | 1332/MURD | 10/06/2025 | 09/08/2025 | PARTHA PRATIM DAS | 22.91 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 3.23 | 4.36 | 100
9 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under HILORA ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000127/2023-2024 | 1914/MEDB | 16/06/2023 | 01/12/2025 | JOGMAYA ENGINEERING | 21.42 | 18.16 | 84.81 | 20
10 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well,120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at HILORA - II & KOHETPUR Water Supply Scheme at Head Work Site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000016/2024-2025 | 1755/MURD | 13/06/2024 | 20/09/2025 | R.K. DRILLING SERVICES | 11.79 | 0 | 0 | 100
Total | [13 empty] | 425.08 | 100.67 | 23.68