## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-II | Berhampore Mechanical | NEZAMPUR PIPED WATER SUPPLY SCHEME. | SM/18185 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under NEZAMPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000079/2023-2024 | 1930/MEDB | 16/06/2023 | 16/09/2023 | M/S S. G. ENTERPRISE | 21 | 0 | 0 | 0
2 | MURSHIDABAD | Suti-II | Murshidabad Division | NEZAMPUR PIPED WATER SUPPLY SCHEME. | SM/18185 | New | Material Requisition To Resource Division |  |  | RTOR000279/2023-2024 | 1230/MURD/19 | 04/05/2023 | 04/05/2023 | Resource Division | 15.35 | 0 | 0 | 0
3 | MURSHIDABAD | Suti-II | Murshidabad Division | NEZAMPUR PIPED WATER SUPPLY SCHEME. | SM/18185 | New | NEZAMPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Suti-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000015/2023-2024 | 979/MURD | 10/04/2023 | 02/04/2025 | M/S. M.S. ENTERPRISE | 207.04 | 9.63 | 4.65 | 30
4 | MURSHIDABAD | Suti-II | Murshidabad Division | NEZAMPUR PIPED WATER SUPPLY SCHEME. | SM/18185 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NEZAMPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000615/2023-2024 | 3387/MURD | 01/11/2023 | 22/11/2023 | TAPAN DAS | 18.56 | 14.94 | 80.51 | 100
5 | MURSHIDABAD | Suti-II | Berhampore Mechanical | NEZAMPUR PIPED WATER SUPPLY SCHEME. | SM/18185 | New | NEW CONNECTION AT NEZAMPUR PH-II |  |  | BILL/01245/2024-2025 |  | 13/12/2024 | 13/12/2024 | WBSEDCL | 4.22 | 0 | 0 | 0
6 | MURSHIDABAD | Suti-II | Berhampore Mechanical | NEZAMPUR PIPED WATER SUPPLY SCHEME. | SM/18185 | New | NEW CONNECTION AT NEJAMPUR PH-1 |  |  | BILL/00633/2024-2025 | 185/WBSEDCL-JJM | 09/08/2024 | 09/08/2024 | WBSEDCL | 3.92 | 0 | 0 | 0
7 | MURSHIDABAD | Suti-II | Berhampore Mechanical | NEZAMPUR PIPED WATER SUPPLY SCHEME. | SM/18185 | New | NEW CONNECTION AT NEZAMPUR PH-1 |  |  | BILL/00617/2024-2025 |  | 02/08/2024 | 02/08/2024 | WBSEDCL | 3.92 | 0 | 0 | 0
8 | MURSHIDABAD | Suti-II | Murshidabad Division | NEZAMPUR PIPED WATER SUPPLY SCHEME. | SM/18185 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 3.83 | 1.51 | 100
Total | [13 empty] | 527.27 | 28.41 | 5.39