## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part - C) | ASSISTANT ENGINEER (HQ) |  | ORD/000201/2023-2024 | 36/KSD | 07/07/2023 | 01/08/2023 | IMAGIN | 4.95 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -D) |  |  | ORD/000665/2023-2024 | 40/KSD | 18/07/2023 | 12/08/2023 | IMAGIN COMMUNICATION | 4.95 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -F) |  |  | ORD/000667/2023-2024 | 42/KSD | 18/07/2023 | 12/08/2023 | IMAGIN COMMUNICATION | 4.95 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -E) |  |  | ORD/000666/2023-2024 | 41/KSD | 18/07/2023 | 12/08/2023 | IMAGIN | 4.95 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -G) |  |  | ORD/000668/2023-2024 | 44/KSD | 20/07/2023 | 14/08/2023 | IMAGIN | 4.93 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -H) |  |  | ORD/000669/2023-2024 | 45/KSD | 20/07/2023 | 14/08/2023 | IMAGIN | 4.94 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part - B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000200/2023-2024 | 33/KSD | 25/06/2023 | 20/07/2023 | S.S.INFRASTRUCTURE | 4.96 | 0 | 0 | 100
8 | MURSHIDABAD |  | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000198/2023-2024 | 32/KSD | 25/06/2023 | 20/07/2023 | IMAGIN | 4.96 | 0 | 0 | 100
9 | MURSHIDABAD |  | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | Support-IEC | Infrastructure support for Information Education & Communication (IEC) activities reached to judicious and safe way of drinking water adopting different modes e.g. display lands, magic show/folk song, leaflet/booklet, school IEC and their documentation through still photography. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000676/2023-2024 | 3683/MURD | 01/12/2023 | 31/12/2023 | IMAGIN | 40.53 | 0 | 0 | 100
10 | MURSHIDABAD |  | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | Support-IEC | Infrastructure support for Information Education & Communication (IEC) activities reached to judicious and safe way of drinking water adopting different modes eg display lands, magic show/folk song, leaflet/booklet, school IEC, formation . and their documentation through still photography in different Gram Panchayat under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,JUNIOR ENGINEER 5 | ORD/000113/2024-2025 | 2386/MURD | 23/08/2024 | 22/09/2024 | IMAGIN | 92.67 | 0 | 0 | 100
Total | [13 empty] | 172.79 | 0 | 0