## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | SIDDHESWARI & ADJOINING MOUJAS PWSS | SM/18312 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 1075/MURD/7 | 19/04/2023 | 19/04/2023 | Resource Division | 20.78 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | SIDDHESWARI & ADJOINING MOUJAS PWSS | SM/18312 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under SIDDHESWARI ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000166/2023-2024 | 2299/MEDB | 04/07/2023 | 04/10/2023 | DAS ENTERPRISE (CHOA) | 23.39 | 19.61 | 83.85 | 60
3 | MURSHIDABAD | Burwan | Murshidabad Division | SIDDHESWARI & ADJOINING MOUJAS PWSS | SM/18312 | New | SIDDHESWARI PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER_BURWAN BLOCK | ORD/000098/2023-2024 | 1721/MURD | 04/07/2023 | 02/04/2025 | M/S. S. DAS AND ENTERPRISE | 443.38 | 279.38 | 63.01 | 80
4 | MURSHIDABAD | Burwan | Murshidabad Division | SIDDHESWARI & ADJOINING MOUJAS PWSS | SM/18312 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SIDDHESWARI & ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER_BURWAN BLOCK | ORD/000379/2023-2024 | 2776/MURD | 01/09/2023 | 22/09/2023 | MAMATA USHA ENTERPRISE | 18.44 | 7.8 | 42.31 | 60
5 | MURSHIDABAD | Burwan | Murshidabad Division | SIDDHESWARI & ADJOINING MOUJAS PWSS | SM/18312 | New | SIDDHESWARI PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER_BURWAN BLOCK | ORD/000518/2023-2024 | 3116/MURD | 05/10/2023 | 31/07/2024 | MOTI RAHAMAN | 407.86 | 85.98 | 21.08 | 10
6 | MURSHIDABAD | Burwan | Berhampore Mechanical | SIDDHESWARI & ADJOINING MOUJAS PWSS | SM/18312 | New | NEW SERVICE CONNECTION AT SIDDESWARI PH 1 C ID 304566361 |  |  | BILL/01479/2024-2025 | 429/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 4.71 | 0 | 0 | 0
Total | [13 empty] | 918.56 | 392.77 | 42.76