## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Tenya Zone - II Water Supply Scheme and Kurulia Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000109/2023-2024 | 1751/MURD | 06/07/2023 | 27/07/2023 | NADIA TUBEWELLS | 27.64 | 13.59 | 49.14 | 50
2 | MURSHIDABAD | Burwan | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | New | KURULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000223/2023-2024 | 2367/MURD | 04/08/2023 | 30/05/2024 | M/S. S. DAS AND ENTERPRISE | 859.33 | 415.3 | 48.33 | 40
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KURULIA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000705/2023-2024 | 2771/MEDB | 25/07/2023 | 25/10/2023 | MENAKA ENTERPRISE | 35.06 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | New | KURULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000576/2023-2024 | 3300/MURD | 20/10/2023 | 01/01/2026 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 261.54 | 0 | 0 | 35
5 | MURSHIDABAD | Burwan | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | New | Providing Functional Household Tap Connections (FHTC) (1222 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Parsalika, Panchhipara & Andulia ( Village Code -315953, 315966, 315967) under Kurulia & Panchhipara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000679/2023-2024 | 3657/MURD | 29/11/2023 | 13/01/2024 | S. DUTTA | 36.75 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | New | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1129/MURD/8 | 25/04/2023 | 25/04/2023 | Resource Division | 38.73 | 0 | 0 | 0
7 | MURSHIDABAD | Burwan | Berhampore Mechanical | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | New | NEW CONNECTION AT KURULIA PH-2 |  |  | BILL/01591/2023-2024 | 429/WBSEDCL-JJM | 12/03/2024 | 12/03/2024 | WBSEDCL | 9.62 | 0 | 0 | 0
8 | MURSHIDABAD | Burwan | Berhampore Mechanical | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | New | NEW CONNECTION AT KURULIA PH-1 |  |  | BILL/01586/2023-2024 | 428/WBSEDCL-JJM | 12/03/2024 | 12/03/2024 | WBSEDCL | 3.82 | 0 | 0 | 0
9 | MURSHIDABAD | Burwan | Berhampore Mechanical | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | New | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Burwan and Kandi block Under District Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000050/2025-2026 | 45/1 | 29/05/2025 | 29/08/2025 | HARA PROSAD DAS | 17.87 | 0 | 0 | 0
Total | [13 empty] | 1290.36 | 428.89 | 33.24