## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. | SM/18364 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 1167/MURD/19 | 28/04/2023 | 28/04/2023 | Resource Division | 22.34 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. | SM/18364 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000350/2022-2023 | 1929/MURD | 19/07/2022 | 01/02/2025 | ENVIROTECH SOLUTIONS | 7.92 | 2.04 | 25.8 | 100
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. | SM/18364 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000349/2022-2023 | 1928/MURD | 19/07/2022 | 01/02/2025 | ENVIROTECH SOLUTIONS | 8.78 | 0.43 | 4.95 | 100
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. | SM/18364 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 400 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Habaspur PWSS in Bhagwagola- I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000658/2023-2024 | 3516/MURD | 09/11/2023 | 01/04/2027 | M/S. GOUTAM CHAKRABORTY | 717.52 | 322.44 | 44.94 | 10
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. | SM/18364 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 31/01/2025 | ENVIROTECH SOLUTIONS | 39.85 | 4.43 | 11.11 | 100
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. | SM/18364 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Lalbagh Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000135/2024-2025 | 2638/MURD | 23/09/2024 | 01/06/2025 | ARJU CONSTRUCTION | 6.14 | 0 | 0 | 40
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. | SM/18364 | Augmentation | NEW CONNECTION AT HABASPUR PH-I |  |  | BILL/01455/2024-2025 | 422/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 11.83 | 0 | 0 | 0
Total | [13 empty] | 814.4 | 329.34 | 40.44