## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18384 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site 3RD Site at LALGOLA Block under Murshidabad Division, P.H. Engineering Dte. |  |  | ORD/000699/2023-2024 | 3784/MURD | 11/12/2023 | 01/01/2024 | GENUINE | 35.34 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18384 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 1167/MURD/17 | 28/04/2023 | 28/04/2023 | Resource Division | 30.59 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18384 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-II under Lalgola ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000650/2023-2024 | 3667/MEDB | 03/11/2023 | 03/02/2024 | M/S K.P. PRAMANIK | 36.25 | 30.42 | 83.9 | 10
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18384 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone- II PWSS in Lalgola Block & Mirzapur (Except Gankar Mouza) PWSS Raghunathganj-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6 | ORD/000612/2023-2024 | 3377/MURD | 31/10/2023 | 30/10/2026 | M/S GHOSH & CO. | 1181.6 | 0 | 0 | 20
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18384 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 31/01/2025 | ENVIROTECH SOLUTIONS | 39.85 | 2.99 | 7.49 | 100
Total | [13 empty] | 1323.63 | 33.4 | 2.52