## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | New | Sahapur (Part-A) & adjoining mouzas PWSS to accommodate Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000143/2023-2024 | 1885/MURD | 17/07/2023 | 01/01/2027 | HOQUEDAR ALI | 256.56 | 35.46 | 13.82 | 25
2 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | New | SAHAPUR (Part-B) & adjoining mouzas PWSS to accommodate Of T/W,LDS, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000147/2023-2024 | 1897/MURD | 17/07/2023 | 11/03/2026 | M/S JAN MAHAMMAD | 520.42 | 188.12 | 36.15 | 20
3 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II & III under SAHAPUR ground water based water supply scheme under Block_ Bharatpur-I, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000711/2023-2024 | 4064/MEDB | 04/12/2023 | 02/08/2025 | CONCORD ENGINEERING | 36.55 | 0 | 0 | 5
4 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAHAPUR AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at BHARATPUR -I Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER,JUNIOR ENGINEER 5 | ORD/000401/2023-2024 | 2808/MURD | 05/09/2023 | 26/09/2023 | INDRAJIT MAZUMDAR | 18.44 | 15.24 | 82.65 | 100
5 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1067/MURD/10 | 18/04/2023 | 18/04/2023 | Resource Division | 52.37 | 0 | 0 | 0
6 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | New | Quotation for Sahapur PH No-1 |  |  | BILL/01434/2023-2024 | 324/WBSEDCL-JJM | 06/02/2024 | 06/02/2024 | WBSEDCL | 12.71 | 0 | 0 | 0
7 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | New | NEW CONNECTION AT SAHAPUR PH-II |  |  | BILL/00403/2024-2025 | 101/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 3.55 | 0 | 0 | 0
8 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | New | RESTORATION OF DAMAGED ROAD CAUSE DUE TO LAYING OF WATER SUPPLY PIPELINE ON SALAR BHARATPUR ROAD TO SIJGRAM LINK ROAD FROM 1.890 KMP TO 2.0 KMP AND 3.50 KMP TO 4.60 KMP UNDER MURSHIDABAD HIGHWAY DIVN-II |  |  | BILL/01634/2024-2025 | 601-MSD/2024-25 | 16/12/2024 | 16/12/2024 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 46.77 | 0 | 0 | 0
9 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | New | Allied & Balance Work for Laying of Distribution System, & Road Restoration Damaged During Laying of UPVC Pipeline at different location of SAHAPUR PWSS in Bharatpur-I Block, of Kandi Sub-Division under Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000253/2024-2025 | 231/MURD | 27/01/2025 | 13/03/2025 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 44.09 | 0 | 0 | 0
10 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | New | NEW CONNECTION AT SAHAPUR PH-III |  |  | BILL/01484/2024-2025 | 454/WBSEDCL-JJM | 27/03/2025 | 27/03/2025 | WBSEDCL | 7.96 | 0 | 0 | 0
Total | [13 empty] | 999.43 | 238.82 | 23.9