## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | BHATPARA AND ADJOINING MOUJAS | SM/18430 | New | BHATPARA & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte.( Scheme ID -PH222362289S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3 | ORD/000193/2023-2024 | 1989/MURD | 21/07/2023 | 20/07/2024 | ASTRA | 789.69 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Murshidabad Division | BHATPARA AND ADJOINING MOUJAS | SM/18430 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 1043/MURD/3 | 17/04/2023 | 17/04/2023 | Resource Division | 208.28 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Berhampore Mechanical | BHATPARA AND ADJOINING MOUJAS | SM/18430 | New | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BHATPARA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001505/2023-2024 | 592/MEDB | 31/01/2024 | 30/04/2024 | HANNAN BUILDERS PVT LTD | 36.83 | 0 | 0 | 0
Total | [13 empty] | 1034.8 | 0 | 0