## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 1067/MURD/11 | 18/04/2023 | 18/04/2023 | Resource Division | 77.6 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | New | Electric Service Connection at GYASABAD PWSS PH I, Application NO.3004407323, ID 304123114 |  |  | BILL/01055/2023-2024 | 186/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 6.81 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | New | NEW CONNECTION AT GAYSABAD PH-II |  |  | BILL/00526/2024-2025 | 163/WBSEDCL-JJM | 29/07/2024 | 29/07/2024 | WBSEDCL | 4.14 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | New | NEW CONNECTION AT GAYSABAD PH-II |  |  | BILL/00517/2024-2025 |  | 08/07/2024 | 08/07/2024 | WBSEDCL | 4.14 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur-I | Central Drilling | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | New | GAYSABAD (Part-B) & adjoining mouzas PWSS to accommodate Of T/W,LDS, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000174/2023-2024 | 1992/MURD | 21/07/2023 | 23/09/2025 | M/S BHUBAN DAS | 418.26 | 171.29 | 40.95 | 10
7 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | New | GAYSABAD (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000202/2023-2024 | 2059/MURD | 27/07/2023 | 01/05/2025 | DHIRENDRANATH MONDAL | 438.55 | 66.69 | 15.21 | 5
8 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II & III under GAYSABAD ground water based water supply scheme under Block_ Bharatpur-I, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000712/2023-2024 | 4065/MEDB | 04/12/2023 | 04/03/2024 | M/S SAJAHAN CHOWDHURY | 36.54 | 23.13 | 63.32 | 5
9 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | New | Balance work for laying of CI/DI pipe line including supporting structure at Gaysabad PWSS at Bharatpur - I Block under Kandi Sub-Division, Murshidabad Division, PHE Dte in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 1 | ORD/000009/2025-2026 | 888/MURD | 22/04/2025 | 20/08/2025 | M/S BHUBAN DAS | 122.18 | 0 | 0 | 0
Total | [13 empty] | 22447.98 | 261.11 | 1.16