## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS | SM/18454 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1210/MURD/39 | 02/05/2023 | 02/05/2023 | Resource Division | 39.23 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS | SM/18454 | New | Laying Distribution System (PART-B), FHTC (PART-A) , Boundary wall for Uncovered of KUNDAL PWSS at JHIKARHATI (PART) (Village Code- 315835) , KUNDAL (Village Code- 315846), PADMALABHBATI (Village Code315845) and JHIKARHATI (PART)in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000192/2023-2024 | 2023/MURD | 25/07/2023 | 22/11/2023 | DIPAYAN DEY | 182.24 | 14.65 | 8.04 | 50
3 | MURSHIDABAD | Burwan | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS | SM/18454 | New | Laying Distribution System (PART-C) and FHTC for KUNDAL PWSS in Burwan Block under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000178/2023-2024 | 1997/MURD | 21/07/2023 | 18/11/2023 | KISMAT ARA BEGAM | 214.39 | 63.55 | 29.64 | 60
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | KUNDAL AND ADJOINING MOUJAS PWSS | SM/18454 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KUNDAL ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000704/2023-2024 | 2770/MEDB | 25/07/2023 | 25/10/2023 | JAL PRAVAHIKA PVT LTD | 35.06 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS | SM/18454 | New | Construction of 450 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, for Uncovered of KUNDAL PWSS at KUNDAL (Village Code- 315846), PADMALABHBATI (Village Code- 315845) in Burwan Block , Kandi Sub-Division under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000190/2023-2024 | 1993/MURD | 21/07/2023 | 01/09/2025 | M/S UNIVERSAL TRADING | 361.74 | 128.44 | 35.51 | 60
6 | MURSHIDABAD | Burwan | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS | SM/18454 | New | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kundal & adjoining mouzas Water Supply Scheme at Head Work Site, 2nd Site & 3 rd site at Burwan Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000203/2023-2024 | 2071/MURD | 28/07/2023 | 04/03/2025 | NADIA TUBEWELLS | 32.03 | 8.5 | 26.55 | 60
7 | MURSHIDABAD | Burwan | Berhampore Mechanical | KUNDAL AND ADJOINING MOUJAS PWSS | SM/18454 | New | NEW SERVICE CONNECTION AT KUNDAL PH 1 C ID 304530174 |  |  | BILL/01476/2024-2025 | 428/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 3.49 | 0 | 0 | 0
8 | MURSHIDABAD | Burwan | Berhampore Mechanical | KUNDAL AND ADJOINING MOUJAS PWSS | SM/18454 | New | NEW SERVICE CONNECTION AT KUNDAL PH 2 C ID 304558999 |  |  | BILL/01475/2024-2025 | 427/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 9.21 | 0 | 0 | 0
Total | [13 empty] | 877.39 | 215.14 | 24.52