## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS | SM/18464 | New | Material Requisition To Resource Division |  |  | RTOR000229/2023-2024 | 1219/MURD/19 | 03/05/2023 | 03/05/2023 | Resource Division | 35.82 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS | SM/18464 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under KHARJJUNA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000703/2023-2024 | 2769/MEDB | 25/07/2023 | 25/10/2023 | DAS ENTERPRISE ( MANGO LANE) | 46.73 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS | SM/18464 | New | NEW SERVICE CONNECTION AT KHARJUNA PH 1 C ID 304391659 |  |  | BILL/00662/2024-2025 |  | 03/09/2024 | 03/09/2024 | WBSEDCL | 3.34 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Murshidabad Division | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS | SM/18464 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHARJJUNA Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3 | ORD/000289/2023-2024 | 2635/MURD | 23/08/2023 | 01/04/2025 | MAMATA USHA ENTERPRISE | 27.67 | 14.57 | 52.65 | 67
5 | MURSHIDABAD | Burwan | Murshidabad Division | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS | SM/18464 | New | KHARJJUNA & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000437/2023-2024 | 2885/MURD | 12/09/2023 | 02/07/2026 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 1366.57 | 298.17 | 21.82 | 35
Total | [13 empty] | 1480.13 | 312.74 | 21.13