## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Raghunathganj - I | Murshidabad Division | CHARKA PIPE WATER SUPPLY SCHEME. | SM/18465 | New | Material Requisition To Resource Division |  |  | RTOR000269/2023-2024 | 1230/MURD/13 | 04/05/2023 |  | Resource Division | 33.69 | 0 | 0 | 0
2 | MURSHIDABAD | Raghunathganj - I | Murshidabad Division | CHARKA PIPE WATER SUPPLY SCHEME. | SM/18465 | New | CHARKA PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Raghunathganj-I Block, Jangipur Sub Division of Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000199/2023-2024 | 2058/MURD | 27/07/2023 | 02/05/2024 | DECON INDIA | 482.22 | 0 | 0 | 0
3 | MURSHIDABAD | Raghunathganj - I | Murshidabad Division | CHARKA PIPE WATER SUPPLY SCHEME. | SM/18465 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 0 | 0 | 100
4 | MURSHIDABAD | Raghunathganj - I | Berhampore Mechanical | CHARKA PIPE WATER SUPPLY SCHEME. | SM/18465 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under CHARKA ground water based water supply scheme under Block_ Raghunathganj-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000680/2023-2024 | 4302/MEDB | 29/12/2023 | 28/03/2024 | DEBJYOTI BASU | 33.53 | 0 | 0 | 0
5 | MURSHIDABAD | Raghunathganj - I | Murshidabad Division | CHARKA PIPE WATER SUPPLY SCHEME. | SM/18465 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHARKA Water Supply Scheme at Head Work Site, 2nd Site site at Raghunathganj ¿ I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,JUNIOR ENGINEER 1 | ORD/000272/2023-2024 | 2603/MURD | 22/08/2023 | 12/09/2023 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 0 | 0
Total | [13 empty] | 821.13 | 0 | 0