## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 1067/MURD/9 | 18/04/2023 | 18/04/2023 | Resource Division | 69.6 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III, IV under INDRANI ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000714/2023-2024 | 4068/MEDB | 04/12/2023 | 04/03/2024 | DAS ENTERPRISE ( MANGO LANE) | 23.44 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Berhampore Mechanical | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II under INDRANI ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000710/2023-2024 | 4063/MEDB | 04/12/2023 | 04/03/2024 | HARA PROSAD DAS | 23.47 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Central Drilling | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). |  |  | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 01/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 0 | 10
5 | MURSHIDABAD | Khargram | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 0 | 0 | 80
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | NEW SERVICE CONNECTION AT INDRANI PH II, ID304233643 |  |  | BILL/01217/2023-2024 | 292/WBSEDCL-JJM | 01/02/2024 | 01/02/2024 | WBSEDCL | 14.12 | 0 | 0 | 0
7 | MURSHIDABAD | Khargram | Berhampore Mechanical | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | NEW SERVICE INDRANI PH1 ID304222223 |  |  | BILL/01148/2023-2024 | 227/WBSEDCL-JJM | 09/01/2024 | 09/01/2024 | WBSEDCL | 4.41 | 0 | 0 | 0
8 | MURSHIDABAD | Khargram | Berhampore Mechanical | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | NEW SERVICE CONNECTION AT INDRANI PH III, ID304233664 |  |  | BILL/01213/2023-2024 | 291/WBSEDCL-JJM | 01/02/2024 | 01/02/2024 | WBSEDCL | 3.36 | 0 | 0 | 0
9 | MURSHIDABAD | Khargram | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | Indrani (Part-B) & adjoining moujas PWSS to accommodate Of T/W,LDS, Pump House Cum Chlorine Room,boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000171/2023-2024 | 1987/MURD | 21/07/2023 | 01/12/2025 | J.S. CONSTRUCTION | 433.05 | 290.83 | 67.16 | 15
10 | MURSHIDABAD | Khargram | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | INDRANI (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000172/2023-2024 | 1988/MURD | 21/07/2023 | 02/12/2025 | DHIRENDRANATH MONDAL | 569.67 | 91.31 | 16.03 | 10
11 | MURSHIDABAD | Khargram | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | New | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur and Indrani Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000670/2022-2023 | 3411/MURD | 22/12/2022 | 01/09/2025 | R.K. DRILLING SERVICES | 8.4 | 0 | 0 | 100
Total | [13 empty] | 1358.06 | 382.14 | 28.14