## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | AOCHA AND ADJJOINING MOUJAS PWSS | SM/18470 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AOCHA AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000285/2023-2024 | 2633/MURD | 23/08/2023 | 13/09/2023 | SARKAR WATER SUPPLY AGENCY | 27.64 | 23.52 | 85.07 | 30
2 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | AOCHA AND ADJJOINING MOUJAS PWSS | SM/18470 | New | Allied & Balance work for Road Restoration of Damaged During Laying of pipeline and Laying of distribution pipe line of AOCHA Piped Water Supply Scheme, Bharatpur-II Block, Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000840/2023-2024 | 818/MURD | 15/03/2024 | 14/05/2024 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 33.81 | 32.68 | 96.67 | 10
3 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | AOCHA AND ADJJOINING MOUJAS PWSS | SM/18470 | New | NEW CONNECTION AT AOUCHA PH-I |  |  | BILL/00471/2024-2025 | 138/WBSEDCL-JJM | 09/07/2024 | 09/07/2024 | WBSEDCL | 3.13 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | AOCHA AND ADJJOINING MOUJAS PWSS | SM/18470 | New | NEW CONNECTION AT AOUCHA PH-I |  |  | BILL/00470/2024-2025 |  | 02/07/2024 | 02/07/2024 | WBSEDCL | 3.13 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | AOCHA AND ADJJOINING MOUJAS PWSS | SM/18470 | New | SHIFTING OF 11 KV AT AOCHA |  |  | BILL/01581/2023-2024 | 427/WBSEDCL-JJM | 12/03/2024 | 12/03/2024 | WBSEDCL | 4.29 | 0 | 0 | 0
6 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | AOCHA AND ADJJOINING MOUJAS PWSS | SM/18470 | New | NEW CONNECTION AT AOCHA PH-II |  |  | BILL/00534/2024-2025 | 179/WBSEDCL-JJM | 06/08/2024 | 06/08/2024 | WBSEDCL | 3.7 | 0 | 0 | 0
7 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | AOCHA AND ADJJOINING MOUJAS PWSS | SM/18470 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under AOCHA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000702/2023-2024 | 2768/MEDB | 25/07/2023 | 01/07/2025 | EASTERN INDIA SALES & SERVICE | 35.18 | 19.39 | 55.11 | 100
Total | [13 empty] | 110.89 | 75.59 | 68.17