## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-II | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | Material Requisition To Resource Division |  |  | RTOR000282/2023-2024 | 1230/MURD/24 | 04/05/2023 | 04/05/2023 | Resource Division | 132.07 | 0 | 0 | 0
2 | MURSHIDABAD | Suti-II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under UMARPUR ground water based water supply scheme under Block_ Suti_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000456/2023-2024 | 3852/MEDB | 06/11/2023 | 06/02/2024 | SURAKSHA | 34.47 | 0 | 0 | 10
3 | MURSHIDABAD | Suti-II | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UMARPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000277/2023-2024 | 2606/MURD | 22/08/2023 | 12/09/2023 | INDRAJIT MAZUMDAR | 27.66 | 0 | 0 | 70
4 | MURSHIDABAD | Suti-II | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | Material Requisition To Resource Division |  |  | RTOR000379/2023-2024 | 495/MURD/02 | 15/02/2024 | 15/02/2024 | Resource Division | 31.56 | 0 | 0 | 0
5 | MURSHIDABAD | Suti-II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-III |  |  | BILL/00168/2024-2025 | 6/WBSEDCL-JJM | 09/04/2024 | 09/04/2024 | WBSEDCL | 3.49 | 0 | 0 | 0
6 | MURSHIDABAD | Suti-II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-III |  |  | BILL/01658/2023-2024 |  | 27/03/2024 | 27/03/2024 | WBSEDCL | 3.49 | 0 | 0 | 0
7 | MURSHIDABAD | Suti-II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-I |  |  | BILL/00170/2024-2025 | 8/WBSEDCL-JJM | 09/04/2024 | 09/04/2024 | WBSEDCL | 3.5 | 0 | 0 | 0
8 | MURSHIDABAD | Suti-II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-II |  |  | BILL/00169/2024-2025 | 7/WBSEDCL-JJM | 09/04/2024 | 09/04/2024 | WBSEDCL | 3.73 | 0 | 0 | 0
9 | MURSHIDABAD | Suti-II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-II |  |  | BILL/01660/2023-2024 |  | 27/03/2024 | 27/03/2024 | WBSEDCL | 3.73 | 0 | 0 | 0
10 | MURSHIDABAD | Suti-II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-I |  |  | BILL/01659/2023-2024 |  | 27/03/2024 | 27/03/2024 | WBSEDCL | 3.5 | 0 | 0 | 0
11 | MURSHIDABAD | Suti-II | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 0 | 0 | 100
Total | [13 empty] | 500.46 | 0 | 0