## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18515 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III ,IV & V ,Zone-III under Lalgola ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000662/2023-2024 | 3711/MEDB | 03/11/2023 | 03/02/2024 | WEST BENGAL ENGINEERING CO. | 58.31 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18515 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 1167/MURD/18 | 28/04/2023 | 28/04/2023 | Resource Division | 49.7 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18515 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000700/2023-2024 | 3785/MURD | 11/12/2023 | 01/01/2024 | SARKAR WATER SUPPLY AGENCY | 35.34 | 0 | 0 | 80
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18515 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 1250 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone -III PWSS in Lalgola Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000649/2023-2024 | 3475/MURD | 07/11/2023 | 05/05/2025 | HANNAN BUILDERS PVT.LTD. | 1434.58 | 0 | 0 | 1
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18515 | Augmentation | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E. Dte. for 03 (Three) Months i.e. from 08.01.2025 to 07.04.2025. (Vehicle No.WB-58AX-9595). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000232/2024-2025 | 05/LSD | 06/01/2025 | 06/04/2025 | BARI ENTERPRISE | 0.44 | 1.18 | 267.59 | 0
Total | [13 empty] | 1578.37 | 1.18 | 0.07