## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti - II | Murshidabad Division | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | New | Material Requisition To Resource Division |  |  | RTOR000252/2023-2024 | 1219/MURD/37 | 03/05/2023 |  | Resource Division | 50.34 | 0 | 0 | 0
2 | MURSHIDABAD | Suti - II | Murshidabad Division | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 0 | 0 | 100
3 | MURSHIDABAD | Suti - II | Berhampore Mechanical | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | New | NEW CONNECTION BAHAGALPUR PH-1 |  |  | BILL/01605/2023-2024 | null | 06/03/2024 |  | WBSEDCL | 4.25 | 0 | 0 | null
4 | MURSHIDABAD | Suti - II | Berhampore Mechanical | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | New | NEW CONNECTION BAHAGALPUR PH-III |  |  | BILL/01576/2023-2024 | 412/WBSEDCL-JJM | 06/03/2024 |  | WBSEDCL | 3.55 | 0 | 0 | 0
5 | MURSHIDABAD | Suti - II | Berhampore Mechanical | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | New | NEW CONNECTION BAHAGALPUR PH-III |  |  | BILL/01576/2023-2024 | 412/WBSEDCL-JJM | 06/03/2024 |  | WBSEDCL | 3.55 | 0 | 0 | 0
6 | MURSHIDABAD | Suti - II | Berhampore Mechanical | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | New | BAHAGALPUR PH-I NEW CONNECTION |  |  | BILL/01485/2023-2024 | 424/WBSEDCL-JJM | 12/03/2024 |  | WBSEDCL | 4.25 | 0 | 0 | 0
7 | MURSHIDABAD | Suti - II | Berhampore Mechanical | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | New | NEW CONNECTION BHAGALPUR PH-II |  |  | BILL/01489/2023-2024 | 411/WBSEDCL-JJM | 06/03/2024 |  | WBSEDCL | 3.3 | 0 | 0 | 0
8 | MURSHIDABAD | Suti - II | Murshidabad Division | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | New | BAHAGALPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000498/2023-2024 | 3053/MURD | 29/09/2023 | 28/09/2024 | ASTRA | 606.64 | 85.43 | 14.08 | 41
9 | MURSHIDABAD | Suti - II | Central Drilling | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 22268.89 | 85.43 | 0.38