## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. | SM/18542 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-II under Bhandara ground water based water supply scheme under Block_Bhagwangola - I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000648/2023-2024 | 3663/MEDB | 03/11/2023 | 03/02/2024 | TARUN KUMAR BHATTACHARYA | 35.9 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. | SM/18542 | Augmentation | Continuation Order Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Executive Engineer under Office of the Executive Engineer, Mechanical/Electrical Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000784/2023-2024 | 3364/AE/MEDB | 27/09/2023 | 27/03/2024 | M/S SAJAHAN CHOWDHURY | 0.9 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. | SM/18542 | Augmentation | Augmentation of BHANDARA (ZONE - II A) & Augmentation of BHAGIRATHPUR PWSS under Jal Jeevan Mission of Bhagawangola-I & Domkal Block, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER |  | ORD/000623/2023-2024 | 3372/MURD | 31/10/2023 | 27/07/2024 | MAMATA USHA ENTERPRISE | 902.27 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. | SM/18542 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000350/2022-2023 | 1929/MURD | 19/07/2022 | 01/02/2025 | ENVIROTECH SOLUTIONS | 7.92 | 0 | 0 | 100
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. | SM/18542 | Augmentation | Augmentation of BHANDARA (ZONE - II B) PWSS under Jal Jeevan Mission of Bhagawangola-I Block, Lalbagh Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3 | ORD/000853/2023-2024 | 829/MURD | 15/03/2024 | 09/01/2025 | CHAKRABORTY CONSTRUCTION | 407.22 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. | SM/18542 | Augmentation | Laying of distribution system for the left out portion of Bhandara Mouza Rising Main with DI pipe and interconnection with DI pipe at Head Work Site of Bhandara Zone - I & II Water Supply Scheme and Ancillary works in Lalbagh Sub Divisional Office under Lalbagh Sub Division, Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000090/2025-2026 | 1829/MURD | 18/08/2025 | 17/10/2025 | MARUTI CONSTRUCTION AND CO. | 47.57 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. | SM/18542 | Augmentation | Continuation Order for Hiring of Maxi cab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E. Dte. for 92 days i.e. from 01.10.2025 to 31.12.2025.(The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)(Vehicle No. WB-58AX-9595) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000153/2025-2026 | 373/LSD | 23/09/2025 | 24/12/2025 | BARI ENTERPRISE | 0.45 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. | SM/18542 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 31/01/2025 | ENVIROTECH SOLUTIONS | 39.85 | 0 | 0 | 100
Total | [13 empty] | 1442.07 | 0 | 0