## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-II | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. | SM/18555 | New | Material Requisition To Resource Division |  |  | RTOR000276/2023-2024 | 1230/MURD/18 | 04/05/2023 | 04/05/2023 | Resource Division | 33.71 | 0 | 0 | 0
2 | MURSHIDABAD | Suti-II | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. | SM/18555 | New | Material Requisition To Resource Division |  |  | RTOR000371/2023-2024 | 495/MURD/10 | 15/02/2024 | 15/02/2024 | Resource Division | 13.53 | 0 | 0 | 0
3 | MURSHIDABAD | Suti-II | Berhampore Mechanical | BHABKI PIPED WATER SUPPLY SCHEME. | SM/18555 | New | BHABKI PH-1 |  |  | BILL/01441/2023-2024 | 334/WBSEDCL-JJM | 07/02/2024 | 07/02/2024 | WBSEDCL | 7.72 | 0 | 0 | 0
4 | MURSHIDABAD | Suti-II | Berhampore Mechanical | BHABKI PIPED WATER SUPPLY SCHEME. | SM/18555 | New | BHABKI PH-II |  |  | BILL/01442/2023-2024 | 335/WBSEDCL-JJM | 07/02/2024 | 07/02/2024 | WBSEDCL | 6.55 | 0 | 0 | 0
5 | MURSHIDABAD | Suti-II | Central Drilling | BHABKI PIPED WATER SUPPLY SCHEME. | SM/18555 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 8 | 0.04 | 11
6 | MURSHIDABAD | Suti-II | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. | SM/18555 | New | BHABKI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- SUTI-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000224/2023-2024 | 2368/MURD | 04/08/2023 | 01/04/2025 | B.B.R.C. INFRASTRUCTURE PVT. LTD. | 495.36 | 46.14 | 9.31 | 12
7 | MURSHIDABAD | Suti-II | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. | SM/18555 | New | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000001/2025-2026 | 761/MURD | 02/04/2025 | 21/06/2025 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0 | 0
8 | MURSHIDABAD | Suti-II | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. | SM/18555 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 6.55 | 2.59 | 100
Total | [13 empty] | 22220.49 | 60.69 | 0.27