## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Samserganj | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. | SM/18556 | New | ANUP NAGAR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur Sub Division Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000232/2023-2024 | 2404/MURD | 07/08/2023 | 03/02/2024 | SUJIT KUMAR SAHA | 428.3 | 0 | 0 | 0
2 | MURSHIDABAD | Samserganj | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. | SM/18556 | New | ANUPNAGAR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur SubDivision Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000250/2023-2024 | 2464/MURD | 09/08/2023 | 08/08/2024 | M/S RUBIET HOSSAIN | 230.08 | 0 | 0 | 0
3 | MURSHIDABAD | Samserganj | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. | SM/18556 | New | Material Requisition To Resource Division |  |  | RTOR000289/2023-2024 | 1230/MURD/32 | 04/05/2023 | 04/05/2023 | Resource Division | 35.78 | 0 | 0 | 0
4 | MURSHIDABAD | Samserganj | Central Drilling | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. | SM/18556 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | MURSHIDABAD | Samserganj | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. | SM/18556 | New | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000001/2025-2026 | 761/MURD | 02/04/2025 | 21/06/2025 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0 | 0
6 | MURSHIDABAD | Samserganj | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. | SM/18556 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 0 | 0 | 100
7 | MURSHIDABAD | Samserganj | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. | SM/18556 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tubewell i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I C, Anup Nagar (CT) & Chachanda Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000119/2023-2024 | 1771/MURD | 06/07/2023 | 20/05/2025 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0 | 40
Total | [13 empty] | 22376.19 | 0 | 0