## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Berhampore Mechanical | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Baidynathpur ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000261/2023-2024 | 3697/MEDB | 03/11/2023 | 03/02/2024 | P. K. ENGINEERING | 23.71 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Murshidabad Division | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | BAIDYNATHPUR & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000222/2023-2024 | 2366/MURD | 04/08/2023 | 01/05/2026 | M/S.TAPAS KUMAR CHAKRABORTY | 867.57 | 173.07 | 19.95 | 10
3 | MURSHIDABAD | Burwan | Murshidabad Division | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAIDYNATHPUR , DHANDANGA & SANTOSHPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000399/2023-2024 | 2806/MURD | 05/09/2023 | 16/04/2025 | INDRAJIT MAZUMDAR | 27.64 | 0 | 0 | 100
4 | MURSHIDABAD | Burwan | Murshidabad Division | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | Material Requisition To Resource Division |  |  | RTOR000232/2023-2024 | 1219/MURD/16 | 03/05/2023 | 03/05/2023 | Resource Division | 9.79 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Berhampore Mechanical | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | Baidyanathpur PH-2 Application No- 3004548228 |  |  | BILL/01175/2023-2024 | 232/WBSEDCL-JJM | 15/01/2024 | 15/01/2024 | WBSEDCL | 4.26 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Berhampore Mechanical | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | Baidyanathpur PH1 Application no-3004548117 |  |  | BILL/01174/2023-2024 | 231/WBSEDCL-JJM | 15/01/2024 | 15/01/2024 | WBSEDCL | 4.05 | 0 | 0 | 0
Total | [13 empty] | 937.02 | 173.07 | 18.47