## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. | SM/18590 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000239/2023-2024 | 1219/MURD/18 | 03/05/2023 |  | Resource Division | 198.03 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. | SM/18590 | Augmentation | Construction of 250 Cum OHR, Pump House, Boundary wall & Repairing of Pump House, B.W, Rising Main Connection & FHTC for Augmentation of PURUSOTTAMPUR PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte.PART_A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000352/2023-2024 | 2674/MURD | 24/08/2023 | 23/08/2024 | M/S BIKASH ENTERPRISE | 342.01 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. | SM/18590 | Augmentation | Augmentation of Ground Water Based Purushottampur PWSS of accommodate Laying Distribution System, in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000293/2023-2024 | 2667/MURD | 24/08/2023 | 20/02/2024 | J.S. CONSTRUCTION | 346.34 | 0 | 0 | 0
Total | [13 empty] | 886.39 | 0 | 0