## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 18/08/2022 | APEX ENGINEERING | 10.79 | 0 | 0 | 100
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Barabil Raghunathpur ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000658/2023-2024 | 3699/MEDB | 09/08/2023 | 09/11/2023 | R.N.S. TRADING | 23.69 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | Augmentation | Augmentation of Ground Water Based Barabil Raghunathpur zone-II PWSS to accommodate FHTC of 176 nos household, Laying Distribution System, Laying Rising Main. at Jalangi Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-A) | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000472/2023-2024 | 3030/MURD | 27/09/2023 | 19/07/2026 | PRADIP KUMAR DAS (PROPRIETORSHIP) | 1039.97 | 434.09 | 41.74 | 91
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | Augmentation | Augmentation of Barabil Raghunathpur Zone-II PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of 200 m, Construction of 400 Cum OHR(1 no) with sub soil investigation , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works, Repair of Boundary Wall at T/W-I site & T/W-II site &Overhauling of R.C.C. elevated reservoir 450 Cum capacity of staging hight 20 mtr under Jal Jeevan Mission of Jalangi Block, Murshidabad District under Murshidabad Division, PHE.Dte. (Part-B) | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000590/2023-2024 | 3332/MURD | 23/10/2023 | 27/11/2025 | ORKID CONSTRUCTION | 217.95 | 63.12 | 28.96 | 50
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 1180/MURD/22 | 29/04/2023 | 29/04/2023 | Resource Division | 290.13 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | Augmentation | Repairing road form Sadikhandiar School More to Fakirabad under Jalangi Block of Augumentatio of Bara Bil Raghunathpur Zone-II Pipe Water Supply Scheme under Murshidabad Division PHE Dte. in District of Murshidabad . |  |  | BILL/01619/2024-2025 | 590-MSD/2024-25 | 11/12/2024 | 11/12/2024 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 15 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | Augmentation | Repairing road form Sadikhandiar School More to Fakirabad under Jalangi Block of Augumentatio of Bara Bil Raghunathpur Zone-II Pipe Water Supply Scheme under Murshidabad Division PHE Dte. in District of Murshidabad . |  |  | BILL/01588/2024-2025 | 590-MSD/2024-25 | 11/12/2024 | 11/12/2024 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 54.99 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | Augmentation | NEW SERVICE CONNECTION AT BARABIL RAGHUNATHPUR PWSS JL 37 PLOT NO 171 ID 304238695 |  |  | BILL/01270/2023-2024 | 290/WBSEDCL-JJM | 01/02/2024 | 01/02/2024 | WBSEDCL | 4.27 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | Augmentation | NEW SERVICE CONNECTION AT BARABIL RAGHUNATHPUR Z I PH 2 C ID 304531192 |  |  | BILL/01644/2024-2025 | 452/WBSEDCL-JJM | 27/03/2025 | 27/03/2025 | WBSEDCL | 3.61 | 0 | 0 | 0
Total | [13 empty] | 1660.39 | 497.2 | 29.94