## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. | SM/18665 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 1180/MURD/23 | 29/04/2023 | 29/04/2023 | Resource Division | 256.66 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. | SM/18665 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Seikhpara ground water based water supply scheme under Block_ Raninagar-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000664/2023-2024 | 3716/MEDB | 03/11/2023 | 03/02/2024 | SUNIL RABIDAS | 22.77 | 14.43 | 63.4 | 50
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. | SM/18665 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 18/08/2022 | APEX ENGINEERING | 10.79 | 2.17 | 20.09 | 100
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. | SM/18665 | Augmentation | Augmentation of Ground Water Based Seikhpara PWSS of accommodate FHTC, Laying Distribution System, Laying Rising Main, Repairing & Construction of Switch Room, Repairing of Boundary Wall, Repairing of 600 CUM OHR, Construction of 400 CUM OHR in Raninagar II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000610/2023-2024 | 3373/MURD | 31/10/2023 | 01/07/2026 | M/S.TAPAS KUMAR CHAKRABORTY | 1378.3 | 337.81 | 24.51 | 20
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. | SM/18665 | Augmentation | Refilling of sand layers, Activated Alumina & existing gravel after washing along with allied works of AIRP at Saikhpara Area (Capacity 100 Cum/hr.) & Muradpur Jalangi Z-I (Capacity 54.00 Cum/hr.) Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000842/2023-2024 | 820/MURD | 15/03/2024 | 14/11/2024 | M/S. S. DAS AND ENTERPRISE | 70.68 | 0.15 | 0.22 | 40
Total | [13 empty] | 1739.19 | 354.57 | 20.39