## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. | SM/18687 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 6.43 | 2.54 | 100
2 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. | SM/18687 | New | Construction of Ground Water Based Srikantabati Part B PWSS of accommodate FHTC(2619 Nos), Laying Distribution System, Laying Rising Main, 400 CUM OHR, Switch Room, Boundary Wall in Raghunathganj- I Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,JUNIOR ENGINEER 1 | ORD/000308/2023-2024 | 2675/MURD | 24/08/2023 | 23/08/2024 | KEYA CONSTRUCTION | 437.95 | 0 | 0 | 0
3 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. | SM/18687 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI PART B & JOTKAMAL ZONE -II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER,JUNIOR ENGINEER 6 | ORD/000620/2023-2024 | 3395/MURD | 01/11/2023 | 22/11/2023 | KALACHAND DAS | 18.4 | 0 | 0 | 100
4 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. | SM/18687 | New | Material Requisition To Resource Division |  |  | RTOR000240/2023-2024 | 1219/MURD/32 | 03/05/2023 | 03/05/2023 | Resource Division | 22.44 | 0 | 0 | 0
5 | MURSHIDABAD | Raghunathganj-I | Berhampore Mechanical | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. | SM/18687 | New | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under SRIKANTABATI, PART B ground water based water supply scheme under Block_ RAGHUNATHGANJ-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000463/2023-2024 | 586/MEDB | 31/01/2024 | 30/04/2024 | M/S. SUPER CONSTRUCTION | 35.75 | 0 | 0 | 0
6 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. | SM/18687 | New | Material Requisition To Resource Division |  |  | RTOR000380/2023-2024 | 495/MURD/01 | 15/02/2024 | 15/02/2024 | Resource Division | 16.13 | 0 | 0 | 0
Total | [13 empty] | 783.92 | 6.43 | 0.82