## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Development of land at Head Work Site of Bahara Water Supply Scheme under Kandi Sub-Division, P.H.Engg. Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001597/2021-2022 | 375/KSD | 19/01/2022 | 18/02/2022 | ROY ENTERPRISE | 4.53 | 0 | 0 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Construction 200 Cum OHR, Laying Distribution System Part-A, FHTC at Brahmanpara Village (Village Code-315290), Bahara Village (Village Code-315291) & Bhandira Village (Village Code-315292), Repairing of Existing Pump house (H.W), Boundary Wall, Existing OHR for Augmentation of BAHARA Ground water based Piped water supply scheme in KANDI Block under Murshidabad Division, PHE. Dte Part-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000248/2023-2024 | 2463/MURD | 09/08/2023 | 01/11/2026 | ROY ENTERPRISE | 182.7 | 78.67 | 43.06 | 21
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Laying Distribution System (PART-B), FHTC work at Dohalia Village (Village Code-315294), Baje Dohalia Village (Village Code-315293) & Bhandira Village (Village Code-315292) for Augmentation of of BAHARA Ground water based Piped water supply scheme in KANDI Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000251/2023-2024 | 2462/MURD | 09/08/2023 | 06/01/2024 | M/S.S.S. ENTERPRISE | 215.67 | 68.93 | 31.96 | 20
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 01/05/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 10.81 | 14.44 | 75
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-II,III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bahara & adjoining mouzas Water Supply Scheme at 2nd & 3 r d Site at K a n d i Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000343/2023-2024 | 2679/MURD | 24/08/2023 | 01/04/2025 | HARUN ALL RASHID & BROTHERS | 21.15 | 0 | 0 | 60
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PUNRAPARA, Augmentation of Bahara & Pacchipara Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000269/2023-2024 | 2587/MURD | 21/08/2023 | 01/11/2024 | INDRAJIT MAZUMDAR | 18.43 | 0 | 0 | 60
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 1004/MURD/9 | 11/04/2023 | 11/04/2023 | Resource Division | 95.05 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1043/MURD/8 | 17/04/2023 | 17/04/2023 | Resource Division | 95.05 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Construction of Valve Chamber, M.S Gate, Laying Distribution System of UPVC Pipeline for Augmentation of Kamalakantapur / Bahara Water Supply Scheme in Bharatpur- I Block, of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000191/2024-2025 | 3148/MURD | 03/12/2024 | 01/10/2026 | ABDUL ENTERPRISE | 45.91 | 0 | 0 | 90
10 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAHARA ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001480/2023-2024 | 760/MEDB | 20/02/2024 | 20/05/2024 | M/S SAJAHAN CHOWDHURY | 36.36 | 0 | 0 | 25
11 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Construction of Boundary wall at 1st Tubewell site of Khasra PWSS & Bahara PWSS of Kandi Block in Kandi Sub-Division under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000196/2024-2025 | 3214/MURD | 09/12/2024 | 01/07/2026 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 12.9 | 0 | 0 | 5
12 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000360/2023-2024 | MURD/439/06 | 08/02/2024 | 08/02/2024 | Resource Division | 4.9 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Design, Drawing, Fabrication, Erection Iron Elimination Plant (IEP) of 45 m3/hr & 40m3/hr Capacity as per Departmental approved model including comossing trial run (3months) of 2 nos Construction of Blower Room (H.W.Site), Pump House (3rd Site), Boundary Wall (3rd Site), Laying of UPVC Pipe of Bahara Water Supply Scheme in Kandi Block of Kandi Sub Division, under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000240/2024-2025 | 190/MURD | 21/01/2025 | 17/03/2026 | ANIRUDDHYA BOSE | 94.01 | 0 | 0 | 30
14 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | Augmentation | Estimate for Restoration of Road damage by PHE pipe line of bituminous pavement and earthen shoulder of Kandi Panchthupi Road (Ch 0.00 KM to 5.00 KM) of Kandi Sub division under Berhampore Division No-I, PWD during 2024-2025. |  |  | BILL/01988/2024-2025 | 630-MSD/24-25 | 18/03/2025 | 18/03/2025 | EXECUTIVE ENGINEER, PWD, BERHAMPORE DIVISION-I | 57.16 | 0 | 0 | 0
Total | [13 empty] | 958.68 | 158.41 | 16.52