## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-I | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | New | Material Requisition To Resource Division |  |  | RTOR000251/2023-2024 | 1219/MURD/36 | 03/05/2023 | 03/05/2023 | Resource Division | 48.16 | 0 | 0 | 0
2 | MURSHIDABAD | Suti-I | Berhampore Mechanical | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under BAHUTULI ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000285/2023-2024 | 4318/MEDB | 29/12/2023 | 29/03/2024 | EASTERN INDIA SALES & SERVICE | 46.88 | 0 | 0 | 10
3 | MURSHIDABAD | Suti-I | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | New | Sinking of 2NOS. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-II Water Supply Scheme and Bahutuli Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000105/2024-2025 | 2195/MURD | 31/07/2024 | 30/08/2024 | SARKAR WATER SUPPLY AGENCY | 23.56 | 0 | 0 | 50
4 | MURSHIDABAD | Suti-I | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | New | Material Requisition To Resource Division |  |  | RTOR000376/2023-2024 | 495/MURD/05 | 15/02/2024 | 15/02/2024 | Resource Division | 23.89 | 0 | 0 | 0
5 | MURSHIDABAD | Suti-I | Berhampore Mechanical | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | New | NEW CONNECTION AT BAHUTALI PH-II |  |  | BILL/00174/2024-2025 | 34/WBSEDCL-JJM | 22/04/2024 | 22/04/2024 | WBSEDCL | 5.25 | 0 | 0 | 0
6 | MURSHIDABAD | Suti-I | Berhampore Mechanical | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | New | NEW CONNECTION AT BAHUTALI PH-II |  |  | BILL/00620/2024-2025 |  | 02/08/2024 | 02/08/2024 | WBSEDCL | 4.4 | 0 | 0 | 0
7 | MURSHIDABAD | Suti-I | Berhampore Mechanical | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | New | NEW CONNECTION AT BAHUTULI PH-II |  |  | BILL/00635/2024-2025 | 189/WBSEDCL-JJM | 12/08/2024 | 12/08/2024 | WBSEDCL | 4.4 | 0 | 0 | 0
8 | MURSHIDABAD | Suti-I | Berhampore Mechanical | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | New | NEW CONNECTION AT BAHUTALI PH-III |  |  | BILL/01241/2024-2025 |  | 11/12/2024 | 11/12/2024 | WBSEDCL | 6.18 | 0 | 0 | 0
9 | MURSHIDABAD | Suti-I | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | New | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000287/2023-2024 | 3176/MURD | 11/10/2023 | 01/01/2026 | CHAKRABORTY CONSTRUCTION | 2258.18 | 0 | 0 | 10
10 | MURSHIDABAD | Suti-I | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 0 | 0 | 100
Total | [13 empty] | 2674.15 | 0 | 0