## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/18694 | Augmentation | Augmentation of Teghari zone II PWSS Construction of 500 Cum OHR with subsoil investigation, Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) (1no)& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) (3 no) & construction of boundary wall of 250 mtr of Raghunathganj - II Block, under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000580/2023-2024 | 3315/MURD | 22/10/2023 | 28/06/2024 | VISION ENTERPRISE | 235.76 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/18694 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 3.96 | 4.86 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/18694 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 1167/MURD/11 | 28/04/2023 | 28/04/2023 | Resource Division | 77.93 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/18694 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000536/2024-2025 | 322/MEDB | 10/02/2025 | 10/05/2025 | SARKAR CONSTRUCTION | 22.73 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/18694 | Augmentation | Laying Distribution System, Rising Main Connection, FHTC connections, for Augmentation of Teghari Zone-II PWSS of Raghunathganj-II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000162/2025-2026 | 2127/MURD | 23/09/2025 | 22/12/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 279.55 | 0 | 0 | 0
Total | [13 empty] | 697.4 | 3.96 | 0.57