## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under Islampur ground water based water supply scheme under Block_ Raninagar-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000661/2023-2024 | 3708/MEDB | 03/11/2023 | 03/02/2024 | R.M.D TRADING | 34.48 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | Augmentation of Islampur PWSS Repairing of Boundary Wall, Pump House & Existing OHR, Construction of 900 Cum OHR, P.H, B.W in Raninagar-I Block , under Murshidabad Division , PHE.Dte.PART_B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000316/2023-2024 | 2673/MURD | 24/08/2023 | 23/08/2024 | M/S. UDYOG AND CO | 335.68 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000233/2023-2024 | 1219/MURD/07 | 03/05/2023 | 03/05/2023 | Resource Division | 551.66 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | Augmentation of Ground Water Based Islampur PWSS of accommodate Providing Functional Household Tap Connection (1394 Nos) in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_C | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000355/2023-2024 | 2669/MURD | 24/08/2023 | 22/11/2023 | M/S B.M. INDUSTRIES | 182.87 | 36.65 | 20.04 | 31
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | Engagement of Consultant for Field Data collection, pipeline network analysis by analyzing actual household demand in pipeline sections, identification of low pressure areas with in the pipe network system and proposing probable solution of the same in 2(Two) nos water supply schemes in Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000071/2024-2025 | 2022/MURD | 11/07/2024 | 21/06/2025 | DHPE | 15.34 | 0 | 0 | 25
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 18/08/2022 | APEX ENGINEERING | 9.6 | 1.96 | 20.39 | 100
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | LOAD ENHANCEMENT ISLAMPUR APPLICATION NO.3004629164 |  |  | BILL/00177/2024-2025 | 13/WBSEDCL-JJM | 16/04/2024 | 16/04/2024 | WBSEDCL | 0.28 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | Restoretion of Road State Highway at Najairpur to Islampore Road from chainge 0.00 kmp to 1.350 km shoulder damage amounting to Rs 637462.00 and Akheriganj to Katlamari road from chainge 8.00 km to 9.30 km. |  |  | BILL/01231/2024-2025 | 492-MSD/2024-25 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER , MURSHIDABAD HIGHWAY DIVISION -I, PWD (ROADS) DIRECT. GOV OF W.B | 34.8 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | Augmentation of Ground Water Based Islampur PWSS Laying Distribution System, Laying Rising Main in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000249/2023-2024 | 2465/MURD | 09/08/2023 | 28/07/2025 | M/S GUHA AND ROY | 333.65 | 110.8 | 33.21 | 25
10 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | Supply of different types C.I Specials at Islampur Sub-Divisional Store for different water supply schemes under Islampur sub-Division, under Murshidabad Division, P.H.E. Dte in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000132/2024-2025 | 2674/MURD | 25/09/2024 | 25/05/2025 | MAKALI ENGINEERING CORPORATION | 32.46 | 8.07 | 24.86 | 100
11 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gaysabad, Kagram, Ranagram, Augmentation of Islampur & Augmentation of Shibnagar Laskarpur Zone - II Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3,JUNIOR ENGINEER 8,JUNIOR ENGINEER_KANDI BLOCK | ORD/000499/2024-2025 | 661/MURD | 19/03/2025 | 05/09/2025 | M/S GUHA AND ROY | 35.27 | 0 | 0 | 100
Total | [13 empty] | 1566.09 | 157.48 | 10.06