## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. | SM/18701 | Augmentation | Demolition of damaged R.C.C. Elevated Reservoir (Capacity 2,72,400 Ltr) at Satitara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000721/2023-2024 | 3874/MURD | 18/12/2023 | 17/01/2024 | DIPAYAN DEY | 5.35 | 5.35 | 100 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. | SM/18701 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000370/2023-2024 | MURD/439/05 | 08/02/2024 | 08/02/2024 | Resource Division | 4.1 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. | SM/18701 | Augmentation | Augmentation of SATITARA under Jal Jeevan Mission of BURWAN Block, Kandi Sub Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000571/2023-2024 | 3291/MURD | 19/10/2023 | 01/10/2025 | M/S. S. DAS AND ENTERPRISE | 1459.34 | 357.09 | 24.47 | 10
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. | SM/18701 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000500/2024-2025 | 664/MURD | 19/03/2025 | 23/05/2025 | NADIA TUBEWELLS | 70.43 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. | SM/18701 | Augmentation | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS SATITARA PWSS Scheme, Block- KANDI to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/002172/2021-2022 | 3260/MURD | 05/10/2021 | 04/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 9.19 | 8.96 | 97.51 | 100
6 | MURSHIDABAD |  | Central Drilling | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. | SM/18701 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 18.28 | 0.09 | 11
Total | [13 empty] | 22888.18 | 389.68 | 1.7