## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. | SM/18702 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 1167/MURD/24 | 28/04/2023 | 28/04/2023 | Resource Division | 17.33 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. | SM/18702 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 2.17 | 2.23 | 80
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. | SM/18702 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000349/2022-2023 | 1928/MURD | 19/07/2022 | 01/02/2025 | ENVIROTECH SOLUTIONS | 8.78 | 2.23 | 25.37 | 100
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. | SM/18702 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Kantanagar PWSS in Bhagwangola-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000586/2023-2024 | 3321/MURD | 22/10/2023 | 01/05/2025 | M/S GUHA AND ROY | 625.7 | 26.72 | 4.27 | 40
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. | SM/18702 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 31/01/2025 | ENVIROTECH SOLUTIONS | 39.85 | 2.57 | 6.44 | 100
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. | SM/18702 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Lalbagh Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000135/2024-2025 | 2638/MURD | 23/09/2024 | 01/06/2025 | ARJU CONSTRUCTION | 6.14 | 0 | 0 | 40
Total | [13 empty] | 795.29 | 33.69 | 4.24