## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. | SM/18704 | Augmentation | Augmentation of Ground Water Based Loknathpur zone-I PWSS to accommodate FHTC of 922 nos household Laying Rising Main ,Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement), Construction of Boundary Wall of 250 m and Soil Investigation & 150 Cum Construction of OHR and Special repair and renovation of existing 2 (Two) Nos Pump House and Boundary wall at Beldanga-II Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000569/2023-2024 | 3290/MURD | 19/10/2023 | 18/10/2024 | VISION ENTERPRISE | 215.41 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. | SM/18704 | Augmentation | Providing , installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I, Zone-I under Loknathpur ground water based water supply scheme under Block_ Beldanga_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000231/2023-2024 | 3668/MEDB | 03/11/2023 | 03/02/2024 | M/S SAJAHAN CHOWDHURY | 11.33 | 0 | 0 | 10
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. | SM/18704 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 13/09/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 0 | 0 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. | SM/18704 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Lokenathpur Zone -I Water Supply Scheme at Head Work Site, 2nd Site site at Beldanga-II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000719/2023-2024 | 3863/MURD | 15/12/2023 | 15/10/2024 | KHOKAN BISWAS | 27.6 | 0 | 0 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. | SM/18704 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000387/2023-2024 | 514/MURD/01 | 16/02/2024 | 16/02/2024 | Resource Division | 90.69 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. | SM/18704 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 1811/MURD/18 | 20/06/2024 | 20/06/2024 | Resource Division | 5.51 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. | SM/18704 | Augmentation | Laying Distribution System for Augmentation of Loknathpur Zone-I (Part-A) PWSS of Beldanga-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000267/2023-2024 | 2575/MURD | 18/08/2023 | 14/02/2024 | SAMBHU NATH ROY | 239.31 | 0 | 0 | 85
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. | SM/18704 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 19/12/2024 | SUJIT MONDAL | 7.27 | 0 | 0 | 0
Total | [13 empty] | 617.08 | 0 | 0