## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 1167/MURD/37 | 28/04/2023 | 28/04/2023 | Resource Division | 153.51 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | Augmentation | Augmentation of BANIAKHALI PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000313/2023-2024 | 2677/MURD | 24/08/2023 | 15/04/2025 | AEF ENTERPRISE (PROP: MAHBUB AKHTAR) | 222.14 | 41 | 18.46 | 20
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold Tap Connection of 03(Three) nos existing commisioned PWSS Domkol Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Katakopra Water Supply Scheme Zone-I & II, Bhagarpur Ramna Water Supply Scheme,Baniakhali & Its Adjoining Mouzas Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER | Junior Engineer | ORD/000345/2022-2023 | 1924/MURD | 19/07/2022 | 18/08/2022 | M/S SOBHA & CO. | 9.09 | 9.06 | 99.65 | 100
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at P.T RASULPUR (PART - A), Kupila and Baniakhali Water Supply Scheme at DOMKAL Block under Murshidabad Division,P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000107/2023-2024 | 1749/MURD | 06/07/2023 | 27/07/2023 | MAMATA USHA ENTERPRISE | 35.37 | 20.38 | 57.63 | 40
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | Augmentation | NEW CONNECTION AT BANIAKHALI Z-II PH-II |  |  | BILL/01109/2024-2025 |  | 14/11/2024 | 14/11/2024 | WBSEDCL | 5.03 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | Augmentation | NEW CONNECTION AT BANIAKHALI Z-II PH-I |  |  | BILL/01108/2024-2025 |  | 14/11/2024 | 14/11/2024 | WBSEDCL | 6.74 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | Augmentation | Augmentation BANIAKHALI PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part -A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000312/2023-2024 | 2676/MURD | 24/08/2023 | 02/04/2027 | J.S. CONSTRUCTION | 459.33 | 238.37 | 51.9 | 40
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | Augmentation | Providing Functional Household Tap Connections ( 665 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Manik Nagar (Village Code -314694) under Domkol Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000637/2023-2024 | 3458/MURD | 06/11/2023 | 06/12/2023 | MOLLA ENTERPRISE (REHENA BIBI) | 18.71 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Baniakhali Piped Water Supply Scheme District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000563/2024-2025 | 345/MEDB | 10/02/2025 | 10/05/2025 | M/S S. S. ENTERPRISE (DOMKAL) | 21.24 | 0 | 0 | 10
Total | [13 empty] | 931.15 | 308.81 | 33.16