## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II , III ,IV & V ,Zone-II under SHIBNAGAR LASKARPUR ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000691/2023-2024 | 4305/MEDB | 29/12/2023 | 29/03/2024 | HARA PROSAD DAS | 55.57 | 25.87 | 46.55 | 5
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | Augmentation | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II) under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3,JUNIOR ENGINEER 8 | ORD/000728/2023-2024 | 4005/MURD | 28/12/2023 | 01/01/2026 | M/S. BIMAL MISRA | 838.96 | 0 | 0 | 35
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shibnagar Laskarpur (Zone - II ) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000358/2023-2024 | 2701/MURD | 25/08/2023 | 15/09/2023 | MAMATA USHA ENTERPRISE | 35.37 | 32.1 | 90.74 | 95
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 24/09/2023 | MERCHANDISE-INDIA | 26.8 | 4.43 | 16.52 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000209/2023-2024 | 1210/MURD/14 | 02/05/2023 | 02/05/2023 | Resource Division | 241.41 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | Augmentation | NEW CONNECTION SHIBNAGAR LASKARPUR Z-II PH-II |  |  | BILL/01614/2023-2024 | 436/WBSEDCL-JJM | 13/03/2024 | 13/03/2024 | WBSEDCL | 6.64 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | Augmentation | NEW CONNECTION SHIBNAGAR LASKARPUR Z-II PH-I |  |  | BILL/01613/2023-2024 | 435/WBSEDCL-JJM | 13/03/2024 | 13/03/2024 | WBSEDCL | 3.81 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | Augmentation | NEW CONNECTION SHIBNAGAR LASKARPUR Z-II PH-III |  |  | BILL/01616/2023-2024 | 437/WBSEDCL-JJM | 13/03/2024 | 13/03/2024 | WBSEDCL | 6.16 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gaysabad, Kagram, Ranagram, Augmentation of Islampur & Augmentation of Shibnagar Laskarpur Zone - II Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3,JUNIOR ENGINEER 8,JUNIOR ENGINEER_KANDI BLOCK | ORD/000499/2024-2025 | 661/MURD | 19/03/2025 | 05/09/2025 | M/S GUHA AND ROY | 35.27 | 0 | 0 | 100
Total | [13 empty] | 1249.99 | 62.39 | 4.99