## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18736 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 04/04/2022 | SAI GEOMETRIC SOLUTION | 28.62 | 4.44 | 15.53 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18736 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000230/2023-2024 | 1219/MURD/20 | 03/05/2023 | 03/05/2023 | Resource Division | 109.49 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18736 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KUPILA Water Supply Scheme and Herampur Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer | ORD/000695/2023-2024 | 3768/MURD | 08/12/2023 | 29/12/2023 | MAMATA USHA ENTERPRISE | 11.79 | 10.55 | 89.49 | 100
4 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18736 | Augmentation | QUOTATION FOR SHIFTING OF 1 NO PHE 25KVA DTR AT HERAMPUR REF ID. 860310611 |  |  | BILL/00652/2024-2025 |  | 16/08/2024 | 16/08/2024 | WBSEDCL | 7.2 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18736 | Augmentation | QUOTATION FOR SHIFTING OF 1 NO PHE 25KVA DTR AT HERAMPUR REF ID. 860310611 |  |  | BILL/00654/2024-2025 | 197/WBSEDCL-JJM | 22/08/2024 | 22/08/2024 | WBSEDCL | 7.2 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18736 | Augmentation | Construction of 700 Cum OHR, Pump House, Boundary wall & Repairing of Pump House for Augmentation of Herampur Zone-I PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte._PART_B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 5 | ORD/000297/2023-2024 | 2647/MURD | 23/08/2023 | 19/11/2025 | SATELLITE CONSTRUCTION | 257.98 | 0 | 0 | 20
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18736 | Augmentation | Augmentation Work Laying Distribution System, Rising Main Connection, FHTC of Herampur Zone-I PWS in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte. (PART - A) | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 5 | ORD/000572/2023-2024 | 3296/MURD | 20/10/2023 | 31/03/2026 | J.S. CONSTRUCTION | 443.2 | 213.95 | 48.28 | 20
Total | [13 empty] | 865.47 | 228.95 | 26.45