## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. | SM/18737 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 1278/MURD/15 | 10/05/2023 | 10/05/2023 | Resource Division | 26.34 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. | SM/18737 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000343/2023-2024 | 79/MURD/10 | 09/01/2024 | 09/01/2024 | Resource Division | 28.5 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. | SM/18737 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000361/2023-2024 | MURD/439/14 | 08/02/2024 | 08/02/2024 | Resource Division | 25.58 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. | SM/18737 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of KHARGRAM ground water based water supply scheme under Block- KHARGRAM Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000056/2023-2024 | 3239/MEDB | 22/08/2023 | 01/07/2025 | DAS ENTERPRISE (CHOA) | 12.27 | 0 | 0 | 40
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. | SM/18737 | Augmentation | Construction of 700 Cum OHR, Boundary Wall, Rising Main Connection, Laying Distribution System PART-A,FHTC at Village- KHARGRAM (Vill. code- 315195) & Village- KANDURI (Vill. code- 315166) for Augmentation of KHARGRAM PWSS in Khargram Block , under Murshidabad Division ,PHE. Dte Part-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000266/2023-2024 | 2572/MURD | 18/08/2023 | 17/07/2025 | M/S. S. DAS AND ENTERPRISE | 393.75 | 0 | 0 | 10
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. | SM/18737 | Augmentation | Laying Distribution System PART-B and FHTC at Vill-KHARGRAM (Village Code-315195) & Vill-DURGAPUR (Village Code-315167) for Augmentation of KHARGRAM PWSS in Khargram Block, under Murshidabad Division ,PHE. Dte Part-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000268/2023-2024 | 2573/MURD | 18/08/2023 | 01/03/2025 | M/S. S. DAS AND ENTERPRISE | 370.63 | 0 | 0 | 5
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. | SM/18737 | Augmentation | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-I,III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Khargram & adjoining mouzas Water Supply Scheme at Head work site & 3rd Site at Khargram Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000359/2023-2024 | 2702/MURD | 25/08/2023 | 01/04/2025 | MAMATA USHA ENTERPRISE | 21.38 | 0 | 0 | 100
Total | [13 empty] | 878.45 | 0 | 0