## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-I PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18740 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 04/04/2022 | SAI GEOMETRIC SOLUTION | 28.62 | 2.83 | 9.89 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-I PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18740 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000262/2023-2024 | 1230/MURD/03 | 04/05/2023 | 04/05/2023 | Resource Division | 20.39 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-I PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18740 | Augmentation | Augmentation of BRINDABANPUR Zone-I Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000273/2023-2024 | 2607/MURD | 22/08/2023 | 01/09/2025 | J.S. CONSTRUCTION | 288.62 | 121.98 | 42.26 | 10
Total | [13 empty] | 337.62 | 124.81 | 36.97