## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/18755 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 3.89 | 4.78 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/18755 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000247/2023-2024 | 1219/MURD/31 | 03/05/2023 | 03/05/2023 | Resource Division | 49.41 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/18755 | Augmentation | Augmentation of Ground Water Based KAKRAMARI (ZONE-I) &KAKRAMARI (ZONE-II) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000568/2023-2024 | 3288/MURD | 19/10/2023 | 16/04/2024 | BIJAY CHOWDHURY | 861.6 | 0 | 0 | 35
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/18755 | Augmentation | KANKRA MARI Z-II PH-II |  |  | BILL/01437/2023-2024 | 332/WBSEDCL-JJM | 07/02/2024 | 07/02/2024 | WBSEDCL | 8.71 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/18755 | Augmentation | KANKRAMARI Z-II PH-1 |  |  | BILL/01438/2023-2024 | 333/WBSEDCL-JJM | 07/02/2024 | 07/02/2024 | WBSEDCL | 5.26 | 0 | 0 | 0
6 | MURSHIDABAD |  | Central Drilling | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/18755 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 22346.17 | 3.89 | 0.02