## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18756 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 04/04/2022 | SAI GEOMETRIC SOLUTION | 28.62 | 2.84 | 9.92 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18756 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000231/2023-2024 | 1219/MURD/13 | 03/05/2023 | 03/05/2023 | Resource Division | 13.89 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18756 | Augmentation | : NEW CONNECTION HERAMPUR PWSS Z2 PH1 ID 304495838 |  |  | BILL/01117/2024-2025 |  | 25/11/2024 | 25/11/2024 | WBSEDCL | 4.34 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18756 | Augmentation | Construction of 250 Cum OHR, Pump House, Boundary wall & Repairing of Pump House for Augmentation of Herampur Zone-I PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1,JUNIOR ENGINEER 5 | ORD/000350/2023-2024 | 2672/MURD | 24/08/2023 | 01/10/2025 | M/S. UNI TRADERS | 143.17 | 26.43 | 18.46 | 30
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18756 | Augmentation | Augmentation of Ground Water Based Herampur Zone-II PWSS in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_A | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 | ORD/000311/2023-2024 | 2671/MURD | 24/08/2023 | 01/04/2025 | CAPITAL CONSTRUCTION | 279.7 | 137.63 | 49.21 | 30
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18756 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000565/2024-2025 | 347/MEDB | 10/02/2025 | 10/05/2025 | SUNIL RABIDAS | 21.38 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18756 | Augmentation | NEW CONNECTION HERAMPUR PWSS Z2 PH1 ID 304495838 |  |  | BILL/01124/2024-2025 | 268/WBSEDCL-JJM | 28/11/2024 | 28/11/2024 | WBSEDCL | 4.34 | 0 | 0 | 0
Total | [13 empty] | 495.45 | 166.91 | 33.69