## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Bhairab Danga village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000433/2023-2024 | 2869/MURD | 11/09/2023 | 10/11/2023 | SAIF TRADERS | 34.71 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Gangin village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000411/2023-2024 | 2835/MURD | 07/09/2023 | 06/11/2023 | PRASANTA BISWAS | 24.4 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Raghupur village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000406/2023-2024 | 2832/MURD | 07/09/2023 | 06/11/2023 | MINA DAS | 34.79 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Raghunathpur village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000417/2023-2024 | 2837/MURD | 07/09/2023 | 06/11/2023 | JYOTI TRADERS | 26.44 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Berbari village, Block:- Bharatpur-I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000468/2023-2024 | 2986/MURD | 21/09/2023 | 20/11/2023 | PAMIR ROY | 33.05 | 0 | 0 | 0
6 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Mas Danga village, Block:- Domkal, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000469/2023-2024 | 2987/MURD | 21/09/2023 | 20/11/2023 | SHIBAM ENTERPRISE | 28.21 | 0 | 0 | 0
7 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Bilkurul village, Block:- Bharatpur-I, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000642/2023-2024 | 3464/MURD | 06/11/2023 | 05/01/2024 | SK CONSTRUCTION (NAJIR SK.) | 30.77 | 0 | 0 | 0
8 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Par Debidaspur village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000829/2023-2024 | 3648/MEDB | 03/11/2023 | 03/02/2024 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0 | 0
9 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Saheb Nagar village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000842/2023-2024 | 3655/MEDB | 03/11/2023 | 03/02/2024 | T. N. BANERJEE | 6.15 | 0 | 0 | 0
10 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bhairab Danga village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000805/2023-2024 | 3624/MEDB | 03/11/2023 | 03/02/2024 | M/S S. S. ENTERPRISE (DOMKAL) | 6.15 | 0 | 0 | 0
11 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bilkurul village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000806/2023-2024 | 3625/MEDB | 03/11/2023 | 03/02/2024 | P. K. ENGINEERING | 6.14 | 0 | 0 | 0
12 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Baje Chuator village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000798/2023-2024 | 3617/MEDB | 03/11/2023 | 03/02/2024 | HARA PROSAD DAS | 6.27 | 0 | 0 | 0
13 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Gangin village, Block:- Suti-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000850/2023-2024 | 3633/MEDB | 03/11/2023 | 03/02/2024 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0 | 0
14 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Jot Sundar village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000811/2023-2024 | 3636/MEDB | 03/11/2023 | 03/02/2024 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0 | 0
15 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bamandasbati village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000801/2023-2024 | 3620/MEDB | 03/11/2023 | 03/02/2024 | ARINDAM MAJUMDAR | 6.27 | 0 | 0 | 0
16 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bazeosmanpur village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000803/2023-2024 | 3622/MEDB | 03/11/2023 | 03/02/2024 | M/S S. S. ENTERPRISE (DOMKAL) | 6.15 | 0 | 0 | 0
17 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Ramdova village, Block:- Suti-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000839/2023-2024 | 3652/MEDB | 03/11/2023 | 03/02/2024 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
18 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Abbhla village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000797/2023-2024 | 3616/MEDB | 03/11/2023 | 03/02/2024 | HARA PROSAD DAS | 6.27 | 0 | 0 | 0
19 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sunda village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000844/2023-2024 | 3657/MEDB | 03/11/2023 | 03/02/2024 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0 | 0
20 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Abbhla village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000643/2023-2024 | 3465/MURD | 06/11/2023 | 05/01/2024 | RURAL CONSTRUCTION | 31.63 | 0 | 0 | 0
21 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Raghunathpur village, Block:- Suti-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000836/2023-2024 | 3650/MEDB | 03/11/2023 | 03/02/2024 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0 | 0
22 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Raghupur village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000838/2023-2024 | 3651/MEDB | 03/11/2023 | 03/02/2024 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
23 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bajitpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000799/2023-2024 | 3618/MEDB | 03/11/2023 | 03/02/2024 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0 | 0
24 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Balichuna village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000800/2023-2024 | 3619/MEDB | 03/11/2023 | 03/02/2024 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
25 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bansbere village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000802/2023-2024 | 3621/MEDB | 03/11/2023 | 03/02/2024 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0 | 0
26 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chator village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000846/2023-2024 | 3629/MEDB | 03/11/2023 | 03/02/2024 | MERCURY ENGINEERING CO | 6.33 | 0 | 0 | 0
27 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Berbari village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000804/2023-2024 | 3623/MEDB | 03/11/2023 | 03/02/2024 | M/S S. S. ENTERPRISE (DOMKAL) | 6.15 | 0 | 0 | 0
28 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Gupura Part-B village, Block:- Bharatpur-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000807/2023-2024 | 3626/MEDB | 03/11/2023 | 03/02/2024 | P. K. ENGINEERING | 6.14 | 0 | 0 | 0
29 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kayemba village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000819/2023-2024 | 3641/MEDB | 03/11/2023 | 03/02/2024 | MASSK ENGINEERING WORKS | 6.15 | 0 | 0 | 0
30 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Jot Raghu village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000810/2023-2024 | 3635/MEDB | 03/11/2023 | 03/02/2024 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0 | 0
31 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Lakshmipur village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000822/2023-2024 | 3643/MEDB | 03/11/2023 | 03/02/2024 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0 | 0
32 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Nagri village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000826/2023-2024 | 3646/MEDB | 03/11/2023 | 03/02/2024 | ALAK KUMAR CHAKRABORTY | 6.15 | 0 | 0 | 0
33 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Lakshmipur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000409/2023-2024 | 2828/MURD | 07/09/2023 | 01/01/2026 | DEBOJYOTI CONSTRUCTION | 24.68 | 0 | 0 | 60
34 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Sudna village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000434/2023-2024 | 2871/MURD | 11/09/2023 | 10/11/2023 | SO-FINE AQUARIUM | 36.59 | 0 | 0 | 50
35 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Bazeosmanpur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000404/2023-2024 | 2829/MURD | 07/09/2023 | 06/11/2023 | KALAM SK. | 24.4 | 0 | 0 | 60
36 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Jot Raghu village, Block:- Farakka, Jangipur Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000470/2023-2024 | 2984/MURD | 21/09/2023 | 01/01/2026 | RAJIB SAHA | 28.21 | 0 | 0 | 30
37 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Kayemba village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer, Estimating Section | ORD/000410/2023-2024 | 2831/MURD | 07/09/2023 | 06/11/2023 | SUPIA CONSTRUCTION | 36.61 | 0 | 0 | 0
38 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Char Juranpur village, Block:- Domkal, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000435/2023-2024 | 2872/MURD | 11/09/2023 | 10/11/2023 | R.S CONSTRUCTION (PART- ROBIN ROY) | 23.3 | 0 | 0 | 0
39 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Ramdova village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000416/2023-2024 | 2836/MURD | 07/09/2023 | 01/01/2026 | K. B. CONSTRUCTION (PROP.KUNTAL BHATTACHARYA) | 26.05 | 0 | 0 | 65
40 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Bamandasbati village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000419/2023-2024 | 2833/MURD | 07/09/2023 | 28/12/2025 | AJOY GHOSH (PROP. SUBHASH GHOSH) | 33.55 | 0 | 0 | 50
41 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Jot Sundar village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000405/2023-2024 | 2830/MURD | 07/09/2023 | 01/01/2026 | FRIENDS CONSTRUCTION | 34.71 | 0 | 0 | 40
42 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Chator village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000407/2023-2024 | 2834/MURD | 07/09/2023 | 01/09/2025 | SUMAN ENTERPRISE AND SUMAN AQUA | 39.37 | 0 | 0 | 25
43 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Balichuna village, Block:- Bharatpur-I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000436/2023-2024 | 2870/MURD | 11/09/2023 | 02/09/2025 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 38.3 | 0 | 0 | 50
44 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Par Debidaspur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000466/2023-2024 | 2988/MURD | 21/09/2023 | 01/03/2025 | PRADIP MAHATO | 37.08 | 0 | 0 | 60
45 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Nagri village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000448/2023-2024 | 2970/MURD | 20/09/2023 | 01/01/2026 | DAS CONSTRACTION (MUNNA DAS) | 28.21 | 0 | 0 | 40
46 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Baje Chuator village, Block:- Bharatpur-I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000467/2023-2024 | 2985/MURD | 21/09/2023 | 01/08/2025 | PARTHA BHASKAR | 36.59 | 0 | 0 | 10
47 | MURSHIDABAD | Bharatpur-I,Domkal,Farakka,Kandi | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | New | Ground Water based mini piped water supply scheme for Saheb Nagar village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000554/2023-2024 | 3215/MURD | 13/10/2023 | 01/01/2026 | BISWAJIT ROY | 29.49 | 0 | 0 | 80
Total | [13 empty] | 871.06 | 0 | 0