## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Kalikapur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000517/2023-2024 | 3612/MURD | 24/11/2023 | 23/01/2024 | KUNTAL SAHA | 31.83 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Srinarayanpur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000494/2023-2024 | 3060/MURD | 29/09/2023 | 28/11/2023 | DAS ENTERPRISE (SUBRATA DAS) | 32.43 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Mamudpur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000522/2023-2024 | 3121/MURD | 05/10/2023 | 04/12/2023 | ASIT KUMAR ROY | 34.58 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Chak Palasi village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000521/2023-2024 | 3120/MURD | 05/10/2023 | 04/12/2023 | SUJIT CHOWDHURY | 19.89 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Saheb Nagar village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000499/2023-2024 | 3080/MURD | 03/10/2023 | 02/12/2023 | NOBEL CONSTRUCTION | 32.52 | 0 | 0 | 0
6 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Durajjay Palsa village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000511/2023-2024 | 3100/MURD | 04/10/2023 | 03/12/2023 | SOUMYA KANTI SINHA | 32.21 | 0 | 0 | 0
7 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Talbona village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000500/2023-2024 | 3081/MURD | 03/10/2023 | 02/12/2023 | ARJU CONSTRUCTION | 32.52 | 0 | 0 | 0
8 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Padmalabhbati village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000519/2023-2024 | 3102/MURD | 04/10/2023 | 03/12/2023 | SANJAY DUTTA | 28.02 | 0 | 0 | 0
9 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Bansbere village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000497/2023-2024 | 3061/MURD | 29/09/2023 | 28/11/2023 | AGNIBESH CHATTERJEE | 24.79 | 0 | 0 | 0
10 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Khansama Danga village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000820/2023-2024 | 3642/MEDB | 03/11/2023 | 03/02/2024 | MASSK ENGINEERING WORKS | 6.15 | 0 | 0 | 0
11 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Mamudpur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000823/2023-2024 | 3644/MEDB | 03/11/2023 | 03/02/2024 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0 | 0
12 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hari Nagar village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000825/2023-2024 | 3645/MEDB | 03/11/2023 | 03/02/2024 | EASTERN INDIA SALES & SERVICE | 6.27 | 0 | 0 | 0
13 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Pachim Srikrishnapur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000828/2023-2024 | 3647/MEDB | 03/11/2023 | 03/02/2024 | ALAK KUMAR CHAKRABORTY | 6.15 | 0 | 0 | 0
14 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Palasi village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000808/2023-2024 | 3627/MEDB | 03/11/2023 | 03/02/2024 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0 | 0
15 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Rasulpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000602/2023-2024 | 3364/MURD | 31/10/2023 | 30/12/2023 | SUDIPTA GHOSH | 34.01 | 0 | 0 | 0
16 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Gopalpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000599/2023-2024 | 3352/MURD | 30/10/2023 | 29/12/2023 | M/S ATISH SINHA | 30.15 | 0 | 0 | 0
17 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Srikrishnapur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000605/2023-2024 | 3366/MURD | 31/10/2023 | 30/12/2023 | M/S MONDAL ASSOCIATES | 32.52 | 0 | 0 | 0
18 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Khansama Danga village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000595/2023-2024 | 3350/MURD | 30/10/2023 | 29/12/2023 | CREATIVE | 24.03 | 0 | 0 | 0
19 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Bajitpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000598/2023-2024 | 3351/MURD | 30/10/2023 | 29/12/2023 | SOUNAK ENTERPRISE | 34.62 | 0 | 0 | 0
20 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Talbona village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000845/2023-2024 | 3658/MEDB | 03/11/2023 | 03/02/2024 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
21 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Srinarayanpur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000843/2023-2024 | 3656/MEDB | 03/11/2023 | 03/02/2024 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
22 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Rasulpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000840/2023-2024 | 3653/MEDB | 03/11/2023 | 03/02/2024 | SURAKSHA | 6.3 | 0 | 0 | 0
23 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Saheb Nagar village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000841/2023-2024 | 3654/MEDB | 03/11/2023 | 03/02/2024 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
24 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kalidaspur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000813/2023-2024 | 3637/MEDB | 03/11/2023 | 03/02/2024 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0 | 0
25 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Pachim Kalidaspur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000814/2023-2024 | 3638/MEDB | 03/11/2023 | 03/02/2024 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
26 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Chak Gupura-Part- B village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000566/2023-2024 | 3276/MURD | 17/10/2023 | 16/12/2023 | FIROJ AHAMMED BISWAS | 22.09 | 0 | 0 | 0
27 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Daspara village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000847/2023-2024 | 3630/MEDB | 03/11/2023 | 03/02/2024 | MERCURY ENGINEERING CO | 6.33 | 0 | 0 | 0
28 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durajjay Palsa village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000848/2023-2024 | 3631/MEDB | 03/11/2023 | 03/02/2024 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0 | 0
29 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Raghunathpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000835/2023-2024 | 3649/MEDB | 03/11/2023 | 03/02/2024 | S.P. ENTERPRISE (BAGUIHATI) | 6.27 | 0 | 0 | 0
30 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kalikapur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000815/2023-2024 | 3639/MEDB | 03/11/2023 | 03/02/2024 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
31 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Gopalpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000809/2023-2024 | 3634/MEDB | 03/11/2023 | 03/02/2024 | SARKAR CONSTRUCTION | 6.3 | 0 | 0 | 0
32 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Kalidaspur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000529/2023-2024 | 3135/MURD | 06/10/2023 | 30/10/2025 | M/S ROY & BOSE ENTERPRISE | 34.81 | 13.37 | 38.41 | 10
33 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Padmalabhbati village, Block- Burwan under ground water based mini piped water supply scheme, Dist- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001488/2023-2024 | 768/MEDB | 20/02/2024 | 20/05/2024 | ARINDAM MAJUMDAR | 6.14 | 0 | 0 | 0
34 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | NEW SERVICE CONNECTION AT PH1 AT RAGHUNATHPUR PO SADAI PS KHARGRAM C ID 304439890 |  |  | BILL/01001/2024-2025 | 218/WBSEDCL-JJM | 13/09/2024 | 13/09/2024 | WBSEDCL | 0.83 | 0 | 0 | 0
35 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | NEW SERVICE CONNECTION AT KATIGRAM, MOUZA KATIGRAM PH 1 MOUZA GURULIA C ID 304440127 |  |  | BILL/01000/2024-2025 |  | 11/09/2024 | 11/09/2024 | WBSEDCL | 0.55 | 0 | 0 | 0
36 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | NEW SERVICE CONNECTION AT KATIGRAM, MOUZA KATIGRAM PH 1 PS KHARGRAM GURULIA ID 304440127 |  |  | BILL/01002/2024-2025 | 219/WBSEDCL-JJM | 13/09/2024 | 13/09/2024 | WBSEDCL | 0.55 | 0 | 0 | 0
37 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | NEW SERVICE CONNECTION AT SAHEBNAGAR MINI PWSS PH 1 ID 304489077 |  |  | BILL/01147/2024-2025 |  | 27/11/2024 | 27/11/2024 | WBSEDCL | 0.67 | 0 | 0 | 0
38 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | NEW SERVICE CONNECTION AT GANGARAMPUR, MOUZA RAHIGRAM PH 1 C ID 304440129 |  |  | BILL/00998/2024-2025 |  | 11/09/2024 | 11/09/2024 | WBSEDCL | 0.79 | 0 | 0 | 0
39 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | NEW SERVICE CONNECTION AT GANGARAMPUR, MOUZA RAHIGRAM PH 1 C ID 304440129 |  |  | BILL/01003/2024-2025 | 220/WBSEDCL-JJM | 13/09/2024 | 13/09/2024 | WBSEDCL | 0.79 | 0 | 0 | 0
40 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | NEW SERVICE CONNECTION AT PH1 AT RAGHUNATHPUR PO SADAI PS KHARGRAM C ID 304439890 |  |  | BILL/00999/2024-2025 |  | 11/09/2024 | 11/09/2024 | WBSEDCL | 0.83 | 0 | 0 | 0
41 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Chak Ramprasad village, Block:- Jalangi, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000510/2023-2024 | 3082/MURD | 03/10/2023 | 02/12/2023 | CHATTERJEE ENTERPRISE | 30.55 | 0 | 0 | 0
42 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Hari Nagar village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000526/2023-2024 | 3122/MURD | 05/10/2023 | 05/12/2025 | SANDESH CONSTRUCTION | 26.83 | 0 | 0 | 0
43 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Daspara village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER_BURWAN BLOCK | ORD/000548/2023-2024 | 3150/MURD | 09/10/2023 | 01/01/2026 | MONDAL CONSTRUCTION | 31.8 | 0 | 0 | 70
44 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Raghunathpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000606/2023-2024 | 3367/MURD | 31/10/2023 | 01/04/2026 | DEBEN RAJAK | 27.1 | 19.23 | 70.94 | 10
45 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Kalidaspur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000567/2023-2024 | 3277/MURD | 17/10/2023 | 18/12/2025 | JIYAUL HAQUE | 32.83 | 0 | 0 | 0
46 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Gangarampur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000849/2023-2024 | 3632/MEDB | 03/11/2023 | 03/02/2024 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0 | 85
47 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Gangarampur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000607/2023-2024 | 3368/MURD | 31/10/2023 | 01/01/2026 | M/S HALDAR CONSTRUCTION (PROP:- ANIRBAN HALDAR ) | 32.52 | 0 | 0 | 90
48 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Katigram village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000817/2023-2024 | 3640/MEDB | 03/11/2023 | 03/02/2024 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 90
49 | MURSHIDABAD | Bharatpur-II,Burwan,Khargram | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | New | Ground Water based mini piped water supply scheme for Katigram village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000604/2023-2024 | 3365/MURD | 31/10/2023 | 01/08/2025 | M/S. BOJLUR RAHAMAN | 26.08 | 22.29 | 85.48 | 40
Total | [13 empty] | 812.94 | 54.89 | 6.75